| Action plan for implementation of the public financial Management reform programme for the period 2026-2030, for the period 2026-2028 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GENERAL OBJECTIVE: ACHIEVING SUSTAINABLE BUDGET WITH A STABLE RATIO OF PUBLIC DEBT TO GDP THROUGH BETTER FINANCIAL MANAGEMENT AND CONTROL, AUDITING AND INTEGRATION OF BUDGET PLANNING WITH GOVERNMENT POLICIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name: | Action plan for Implementation of the Public Financial Management Reform Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for monitoring and control of implementation: | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Public policy document for which the action plan is determined: | Public Financial Management Reform Programme 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Public policy umbrella document: | Public Administration Reform Strategy 2021-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at general objective level (outcome indicator) | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |
| Real GDP growth | Percentage (%) |  |  |  |  |  |  |  |  |  | Fiscal Strategy, Economic Reform Program |  |  |  |  |  |  | 3,9% |  |  |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3% |  |  |  |  |  |  |  |  |  |  | 5% |  |  |  |  |  |  |  |  |  | 3,5% |  |  |  |  |  |
| General government debt level in GDP | Percentage (%) |  |  |  |  |  |  |  |  |  | Fiscal Strategy, Economic Reform Program |  |  |  |  |  |  | 46,9 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 44,5% |  |  |  |  |  |  |  |  |  |  | 44,3% |  |  |  |  |  |  |  |  |  | 44,1% |  |  |  |  |  |
| SPECIFIC OBJECTIVE I: CAPACITY FOR BUDGET PLANNING AND PUBLIC INVESTMENT MANAGEMENT IMPROVED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at specific objective level (outcome indicator) | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |
| General Government deficit up to 3% of GDP | Percentage (%) |  |  |  |  |  |  |  |  |  | Revised Fiscal Strategy |  |  |  |  |  |  | 2% |  |  |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3% |  |  |  |  |  |  |  |  |  |  | 3% |  |  |  |  |  |  |  |  |  | 2,5% |  |  |  |  |  |
| Measure 1.1: Improvement of the Programme Budget and Medium-term Expenditure Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure | Link to program budget |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IPA2021 and donor funds | - |  |  |  |  |  |  |  |  |  | 2026: 85.000 |  |  |  |  |  |  |  |  |  |  |  | 2027: 2.400 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 20.400 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Informative and educational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |
| Percentage of healthcare institutions applying the programme budget | Percentage (%) |  |  |  |  |  |  |  |  |  | Software for budget preparation of healthcare institutions |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | 70% |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |  |
| Activity name: | Deadline for completion of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  | Partners in the implementation of activity |  |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of financing |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  |  |
| 1.1.1 Introduction of program budget in healthcare institutions | Q4 2026 |  |  |  |  | Ministry of Finance |  |  |  |  | Republic fund of health insurance |  |  |  |  |  |  | IPA2021 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 85.000 |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| 1.1.2 Development of methodologies and manuals for the preparation of program budgets and reporting on program performance at all levels of government | Q4 2027 |  |  |  |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | 2.400* |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| 1.1.3 Improvement of modules for monitoring and evaluation of program performance and preparation of a consolidated performance report | Q4 2028 |  |  |  |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | 1.200* + 12.000* |  |  |  |  |  |
| 1.1.4 Improvement of the system and development models for more credible expenditure projections and increased budget transparency | Q4 2028 |  |  |  |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | 1.200* + 6.000* |  |  |  |  |  |
| Measure 1.2: Strengthening institutional capacities and improving the methodological framework for green budgeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure | Link to program budget |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Donor funds | - |  |  |  |  |  |  |  |  |  | 2026: 1.560 |  |  |  |  |  |  |  |  |  |  |  | 2027: 1.560 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 3.780 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |
| Coverage of the application of the green budgeting methodology across all levels of government | Percentage (%) |  |  |  |  |  |  |  |  |  | Ministry of Finance report |  |  |  |  |  |  | 50% |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 50% |  |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |  |
| Activity name: | Deadline for completion of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  | Partners in the implementation of the activity |  |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of financing |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  |  |
| 1.2.1 Organization of workshops for budget analysts to strengthen capacities for green budgeting | 4Q 2028 |  |  |  |  | Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 780* |  |  |  |  |  |  |  |  |  |  | 780* |  |  |  |  |  |  |  |  |  | 780* |  |  |  |  |  |
| 1.2.2 Expansion of the scope of the green budgeting methodology in terms of types of expenditures and levels of government | 4Q 2028 |  |  |  |  | Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | 900* |  |  |  |  |  |
| 1.2.3 Strengthening the capacities of the green budgeting working group through training and workshops | 4Q 2028 |  |  |  |  | Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 780* |  |  |  |  |  |  |  |  |  |  | 780* |  |  |  |  |  |  |  |  |  | 780* |  |  |  |  |  |
| 1.2.4. Study visit – example of good practice in green budgeting | 4Q 2028 |  |  |  |  | Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | 1.320* |  |  |  |  |  |
| Measure 1.3: Harmonization of the budget process in the Republic of Serbia with the budget process in the European Union |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure | Link to program budget |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Donor funds | - |  |  |  |  |  |  |  |  |  | 2026: - |  |  |  |  |  |  |  |  |  |  |  | 2027: 2.400 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Informative and educational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |
| Percentage of trained budget analysts in the Ministry of Finance | Percentage (%) |  |  |  |  |  |  |  |  |  | Ministry of Finance report |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 80% |  |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| Activity name: | Deadline for completion of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  | Partners in the implementation of activity |  |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  |  |
| 1.3.1 Analyses of the budget preparation process in the Republic of Serbia and its alignment with the budget process in EU countries | Q4 2027 |  |  |  |  | Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | 1.200* |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| 1.3.2 Development of guidelines for harmonizing the budget process with EU standards | Q4 2028 |  |  |  |  | Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | 600* |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| 1.3.3 Strengthening the capacities of budget analysts for budget preparation in accordance with EU regulations | Q4 2028 |  |  |  |  | Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | 600* |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| Measure 1.4: Improvement of the environment for efficient management of capital projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure | Link to program budget |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Donor funds | - |  |  |  |  |  |  |  |  |  | 2026: 4.900 |  |  |  |  |  |  |  |  |  |  |  | 2027: 1.600 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 100 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Department for Capital projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Regulatory |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |
| Percentage of capital projects included in the budget, subject to assessment and evaluated in accordance with the methodology governing capital projects | Percentage (%) |  |  |  |  |  |  |  |  |  | Budget law/Commission for Capital Investments |  |  |  |  |  |  | 60% |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 70% |  |  |  |  |  |  |  |  |  |  | 80% |  |  |  |  |  |  |  |  |  | 90% |  |  |  |  |  |
| Activity name: | Deadline for completion of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  | Partners in the implementation of activity |  |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  |  |
| 1.4.1 Amendments and supplements to the legal framework in accordance with identified weaknesses in practical implementation | Q4 2026 |  |  |  |  | Ministry of Finance |  |  |  |  | World Bank, SECO, IMF |  |  |  |  |  |  | Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2.400 |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| 1.4.2 Improvement and standardization of public reports on the status of capital projects monitored in accordance with the methodology | Q4 2027 |  |  |  |  | Ministry of Finance |  |  |  |  | World Bank, SECO, IMF |  |  |  |  |  |  | Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | 1.000 |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| 1.4.3 Familiarization of the officials from Department for Capital Projects with good international practices related to planning, monitoring, and reporting in the field of public investments through a study visit and the organization of a workshop for employees of the Department for Capital Projects and other departments | Q4 2026 |  |  |  |  | Ministry of Finance |  |  |  |  | World Bank, SECO, IMF |  |  |  |  |  |  | Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2.500 |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| 1.4.4 Preparation of a manual on the methodology in the field of capital projects (design, preparation for printing, proofreading, consulting support for content) | Q1 2028 |  |  |  |  | Ministry of Finance – Department for Capital Projects |  |  |  |  | SECO |  |  |  |  |  |  | Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | 600 |  |  |  |  |  |  |  |  |  | 100 |  |  |  |  |  |
| Measure 1.5: Strengthening the capacities of the Section for fiscal risk monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure | Link to program budget |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS and donor funds | 2301-0013 |  |  |  |  |  |  |  |  |  | 2026: 28.350 |  |  |  |  |  |  |  |  |  |  |  | 2027: 25.200 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 14.700 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Budget department, Section for fiscal risk monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |  |
| Published report on fiscal risks | Published/Not published |  |  |  |  |  |  |  |  |  | Ministry of Finance website |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  | Published |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Published |  |  |  |  |  |  |  |  |  | Published |  |  |  |  |  |  |
| Amendments and additions of the Unified Methodology for Monitoring Fiscal Risks in the Republic of Serbia | Adopted/Not adopted |  |  |  |  |  |  |  |  |  | Official gazette of the Republic of Serbia |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | Adopted |  |  |  |  |  |  |
| Activity name: | Deadline for completion of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  | Partners in the implementation of activity |  |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  |  |
| 1.5.1 Improvement and standardization of reporting on fiscal risks | Q4 2026 |  |  |  |  | Ministry of Finance – Budget Department, Section for fiscal risk monitoring |  |  |  |  | World Bank |  |  |  |  |  |  | Budget of RS, Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 16.800 |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| 1.5.2 Revision of the methodology for monitoring fiscal risks related to the operations of state-owned enterprises and local self-governments | Q4 2027 |  |  |  |  | Ministry of Finance – Budget Department, Section for fiscal risk monitoring |  |  |  |  | World Bank |  |  |  |  |  |  | Budget of RS, Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  | 2301-0013 (Regular allocations) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 4.200 |  |  |  |  |  |  |  |  |  |  | 12.600 |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| 1.5.3 Development of methodology for linking budget reserves with quantified risk indicators | Q4 2028 |  |  |  |  | Ministry of Finance – Budget Department, Section for fiscal risk monitoring |  |  |  |  | World Bank |  |  |  |  |  |  | Budget of RS, Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  | 2301 -0013 (Regular allocations) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 7.350 |  |  |  |  |  |  |  |  |  |  | 8.400 |  |  |  |  |  |  |  |  |  | 9.450 |  |  |  |  |  |
| 1.5.4 Development of a methodology for monitoring fiscal risks from climate change | Q4 2028 |  |  |  |  | Ministry of Finance – Budget Department, Section for fiscal risk monitoring |  |  |  |  | World Bank |  |  |  |  |  |  | Budget of RS, Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  | 2031-0013 (Regular allocations) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | 4.200 |  |  |  |  |  |  |  |  |  | 5.250 |  |  |  |  |  |
| Measure 1.6: Establishment of a system for coordination and management of EU own resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure | Link to program budget |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS and IPA2022 | 2301-0012 |  |  |  |  |  |  |  |  |  | 2026: 85.000 |  |  |  |  |  |  |  |  |  |  |  | 2027: 110.000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 50.000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Macroeconomic and fiscal projections and analyses department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2028. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Informative and educational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |  |  |  |
| Level of progress within Negotiation chapter 33 | 1. No progress achieved 2. Limited progress 3. Some progress |  |  |  |  |  |  |  |  |  | European Commission’s annual report on Serbia |  |  |  |  |  |  | 1. No progress achieved |  |  |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  | 2. Limited progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3. Some progress |  |  |  |  |  |  |  |  |  | 3. Some progress |  |  |  |  |  |  |  |  |
| Activity name: | Deadline for completion of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  | Partners in the implementation of the activity |  |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  |  |
| 1.6.1 Establishment of operational and procedural links between institutions with the aim of improving coordination and data exchange in accordance with the obligations of Chapter 33 | Q4 2026 |  |  |  |  | Ministry of Finance |  |  |  |  | Statistical office of the Republic of Serbia, Tax Administration, Customs Administration, NBS, Treasury Administration, Ministry of environmental protection, Enviromental protection agency |  |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| 1.6.2 Development and improvement of systems, processes and procedures in organizational and informational, i.e. technical and technological terms | Q4 2028 |  |  |  |  | Ministry of Finance |  |  |  |  | Statistical office of the Republic of Serbia, Tax Administration, Customs Administration, NBS, Treasury Administration, Ministry of environmental protection, Enviromental protection agency |  |  |  |  |  |  | IPA2022 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 60.000 |  |  |  |  |  |  |  |  |  |  | 60.000 |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| 1.6.3 Establishment and development of administrative capacities through the creation of appropriate organizational units, recruitment, and training | Q4 2028 |  |  |  |  | Ministry of Finance |  |  |  |  | Statistical office of the Republic of Serbia, Tax Administration, Customs Administration, NBS, Treasury Administration, Ministry of environmental protection, Enviromental protection agency |  |  |  |  |  |  | Budget of RS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 25.000 |  |  |  |  |  |  |  |  |  |  | 50.000 |  |  |  |  |  |  |  |  |  | 50.000 |  |  |  |  |  |
| Measure 1.7: Improvement of medium-term planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure | Link to program budget |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS | 0610-0006 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Public policy secretariat (PPS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2028. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Informative and educational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |
| Number of adopted and published medium-term plans of entities obliged to conduct medium-term planning at the republic level | Number |  |  |  |  |  |  |  |  |  | Websites of entities obliged to conduct medium-term planning |  |  |  |  |  |  | 29 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 30 |  |  |  |  |  |  |  |  |  |  | 32 |  |  |  |  |  |  |  |  |  | 34 |  |  |  |  |  |
| Percentage of published reports on the implementation of medium-term plans in relation to the total number of published medium-term plans valid for the year being reported on | Percentage % |  |  |  |  |  |  |  |  |  | Websites of entities obliged to conduct medium-term planning |  |  |  |  |  |  | 93% |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 95% |  |  |  |  |  |  |  |  |  |  | 95% |  |  |  |  |  |  |  |  |  | 95% |  |  |  |  |  |
| Activity name: | Deadline for completion of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  | Partners in the implementation of activity |  |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  |  |
| 1.7.1 Providing systematic mentoring support for the preparation of medium-term plans of entities subject to medium-term planning at the national level, in order to achieve better alignment with the entities’ annual budgets | Q4 2028 |  |  |  |  | PPS |  |  |  |  | Entities obliged to conduct medium-term planning |  |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  | 0610-0006 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| 1.7.2 Establishment of a network of medium-term planning coordinators to improve the alignment of public policy planning with the medium-term expenditure framework | Q4 2028 |  |  |  |  | PPS |  |  |  |  | Entities obliged to conduct medium-term planning |  |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  | 0610-0006 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| SPECIFIC OBJECTIVE II: EFFICIENT COLLECTION AND MANAGEMENT OF BUDGET FUNDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at specific objective level (outcome indicator) | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |
| Actual revenues and expenditures of the state sector budget on an annual basis are within 5% of those projected in the fiscal strategy | Percentage (%) |  |  |  |  |  |  |  |  |  | Fiscal strategy |  |  |  |  |  |  | Within the range of up to 5% |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Within the range of up to 5% |  |  |  |  |  |  |  |  |  |  | Within the range of up to 5% |  |  |  |  |  |  |  |  |  | Within the range of up to 5% |  |  |  |  |  |
| Measure 2.1: Efficient collection of budget revenues under the competence of the Tax Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure | Link to program budget |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 (Note: within this measure, certain activities are presented as a cumulative total for two or three years. For the purpose of completing the table below, these funds have been distributed evenly across the years, although this may not necessarily reflect the situation in practice.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Loan, IPA2021, IPA2022, Donor funds | - |  |  |  |  |  |  |  |  |  | 2026: 1.680.980,95 |  |  |  |  |  |  |  |  |  |  |  | 2027: 1.860.778,97 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 2.958.827 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance - Tax Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) | Unite of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |
| Percentage of realized collection compared to the approved budget estimate (personal income tax, corporate income tax, gross domestic VAT, gross excises) | Percentage (%) |  |  |  |  |  |  |  |  |  | Budget Law and Tax administration report |  |  |  |  |  |  | 104,4% |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |  |
| Activity name: | Deadline for completion of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  | Partners in the implementation of activity |  |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  |  |  |  |  |
| 2.1.1 Implementation of a ready-made commercial solution for an Integrated Tax Management Information System (COTS-ITMS) | Q4 2028 |  |  |  |  | Ministry of Finance - Tax administration |  |  |  |  |  |  |  |  |  |  |  | Law on the ratification of Loan agreement (additional financing for TAMP, loan 8936-YF) between the Republic of Serbia and International bank for reconstruction and development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.513.250 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.793.662 |  |  |  |  |  |  |  |  |  | 2.943.071 |  |  |  |  |  |  |  |  |
| 2.1.2 Improved educational function within the Tax Administration of the Republic of Serbia | Q2 2027 |  |  |  |  | Ministry of Finance - Tax administration |  |  |  |  |  |  |  |  |  |  |  | IPA 2022 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 74.074 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 18.000 |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |
| 2.1.3 Further harmonization of national legislation and development of a roadmap relevant for supporting the implementation of international information exchange systems | Q4 2027 |  |  |  |  | Ministry of Finance - Tax administration |  |  |  |  |  |  |  |  |  |  |  | IPA 2021 (UNDP) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 49.500 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5.610 |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |
| 2.1.4 Enhanced strategic competencies for human resource management | Q2 2027 |  |  |  |  | Ministry of Finance - Tax administration |  |  |  |  |  |  |  |  |  |  |  | Donor funds |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  | 650* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |
| 2.1.5 Introduction of a preliminary VAT return through the upgrade of the e-Invoice system | Q1 2027 |  |  |  |  | Ministry of Finance - Department for digitalization in the field of finance |  |  |  |  | Tax administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Data not available |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Data not available |  |  |  |  |  |  |  |  |  | Data not available |  |  |  |  |  |  |  |  |
| 2.1.6 Improvement of the e-Delivery Note system | Q4 2027 |  |  |  |  | Ministry of Finance - Department for digitalization in the field of finance |  |  |  |  | Inspection authorities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Data not available |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Data not available |  |  |  |  |  |  |  |  |  | Data not available |  |  |  |  |  |  |  |  |
| 2.1.7 Further enhancement of the eExcise system | Q1 2027 |  |  |  |  | Ministry of Finance - Department for digitalization in the field of finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Data not available |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Data not available |  |  |  |  |  |  |  |  |  | Data not available |  |  |  |  |  |  |  |  |
| 2.1.8 Harmonization of selected tax laws of the Republic of Serbia (VAT, Personal Income Tax, Corporate Income Tax, Excise Duties, and the Law on Tax Procedure and Tax Administration) with the EU acquis communautaire (Chapter 16 – Taxation) | Q4 2026 |  |  |  |  | Ministry of Finance – Department for Fiscal System |  |  |  |  | Tax administration |  |  |  |  |  |  | IPA 2021 PFM FF/Bilateral support from Slovakia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 55.501,95 for both years |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.9 Drafting of accompanying by-laws | Q4 2028 |  |  |  |  | Ministry of Finance – Department for Fiscal System |  |  |  |  | Tax administration |  |  |  |  |  |  | IPA 2021 PFM FF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total of 37.800 for three years |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.10 Preparation of a change management plan and capacity building for the business community regarding the practical implementation of fiscal regulations | Q4 2028 |  |  |  |  | Ministry of Finance – Department for Fiscal System |  |  |  |  | Tax administration |  |  |  |  |  |  | IPA 2021 PFM FF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total of 9.468 for three years |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.11 Establishment of a central factoring registry | Q2 2028 |  |  |  |  | Ministry of Finance, Department for digitalization in the field of finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Data not available |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 2.2: Reduction of administrative burden and improvement of efficiency in providing electronic services under the competence of Tobacco administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure | Link to program budget |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS | 2301-0010 |  |  |  |  |  |  |  |  |  | 2026: 350 |  |  |  |  |  |  |  |  |  |  |  | 2027:- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028:- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance - Tobacco administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Informative and educational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |
| Percentage of business entities submitting reports electronically via the portal | Percentage (%) |  |  |  |  |  |  |  |  |  | Portal for electronic submission of reports |  |  |  |  |  |  | 60% |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 70% |  |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |  |
| Activity name: | Deadline for completion of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  | Partners in the implementation of activity |  |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  |  |
| 2.2.1 Preparation, publication, and implementation of video trainings and guidelines to support business entities in using the portal | Q4 2026 |  |  |  |  | Tobacco administration |  |  |  |  |  |  |  |  |  |  |  | Budget of RS 2301-0010 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 350 |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| 2.2.2 Improvement of the efficiency of processing reports submitted through the portal | Q4 2027 |  |  |  |  | Tobacco administration |  |  |  |  |  |  |  |  |  |  |  | 2301 Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| Measures 2.3: Strengthening the administrative capacities of the Customs administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure |  | Link to program budget |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS, IPA (unallocated), IPA2020, IPA 2021, IPA2026, donor funds |  | 7081 5013 |  |  |  |  |  |  |  |  |  | 2026: 675.335,42 |  |  |  |  |  |  |  |  |  |  |  | 2027: 548.453,72 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Customs administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2028 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) |  | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |
| Percentage of realized collection of customs duties in relation to the projected budget estimate |  | Percentage (%) |  |  |  |  |  |  |  |  |  | Law on budget |  |  |  |  |  |  | Customs 101,64% |  |  |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |
| Percentage of realized collection of import VAT in relation to the projected budget estimate |  | Percentage (%) |  |  |  |  |  |  |  |  |  | Law on budget |  |  |  |  |  |  | VAT 97,72% |  |  |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  | 100% |  |  |  |  |
| Activity name: |  | Deadline for completion of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  | Partners in the implementation of activity |  |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  |  |  |  |
| 2.3.1 Upgrade of the NCTS transit procedure application |  | Q4 2028 |  |  |  |  | Customs administration |  |  |  |  | - |  |  |  |  |  |  | Budget of RS – An amount of 36 million dinars was paid in 2025, PA 0002 – Support to the customs service information system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |
| 2.3.2 Improvement of capacities for effective post-clearance audits, determination of customs value, preferential origin, and classification of goods |  | Q4 2027 |  |  |  |  | Customs administration |  |  |  |  |  |  |  |  |  |  |  | IPA unallocated Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 14.400 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 105.600* |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |
| 2.3.3 Modernization of the customs laboratory |  | Q4 2027 |  |  |  |  | Customs administration |  |  |  |  |  |  |  |  |  |  |  | IPA2026 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 360.000 |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |
| 2.3.4 Implementation of import and export automated systems (AIS-AES) and control system (CDS) |  | Q4 2027 |  |  |  |  | Customs administration |  |  |  |  |  |  |  |  |  |  |  | IPA2020 |  |  |  |  |  |  |  |  |  |  |  | 7081 |  |  |  |  |  |  |  |  | 363.320 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |
| 2.3.5 Development of a system for collection of budget revenues, collection monitoring, and integration with automated systems |  | Q4 2027 |  |  |  |  | Customs administration |  |  |  |  |  |  |  |  |  |  |  | Budget of RS |  |  |  |  |  |  |  |  |  |  |  | PA 0002 |  |  |  |  |  |  |  |  | 72.000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 60.000 |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |
| 2.3.6 Implementation of software for integrated tariff management (ITMS) |  | Q1 2027 |  |  |  |  | Customs administration |  |  |  |  |  |  |  |  |  |  |  | IPA2021 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 217.115,42 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 22.853,72 |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |
| 2.3.7 Procurement and implementation of a data warehouse for storing customs data |  | Q4 2027 |  |  |  |  | Customs administration |  |  |  |  |  |  |  |  |  |  |  | IPA2021 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 8.500 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |
| Measure 2.4: Efficient public debt management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure |  | Link to program budget |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS and donor funds |  | 2201-0004 |  |  |  |  |  |  |  |  |  | 2026: - |  |  |  |  |  |  |  |  |  |  |  | 2027: - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 15.000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Public debt administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) |  | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |
| Share of interest expenditures in GDP |  | Percentage (%) |  |  |  |  |  |  |  |  |  | Annual report on work of Public debt administration |  |  |  |  |  |  | 1,9% |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,9% |  |  |  |  |  |  |  |  |  | 1,9% |  |  |  |  |  |  |  |  |  | 1,9% |  |  |  |  |
| Activity name: |  | Deadline for completion of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  | Partners in the implementation of activity |  |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  |
| 2.4.1 Expansion of reporting scope (units) through development and implementation of an Information System for submission of financial reports |  | Q4 2027 |  |  |  |  | Public debt administration |  |  |  |  | - |  |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  | 2201 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |
| 2.4.2 Issuance of green/sustainable Eurobonds on the international market |  | Q2 2026 |  |  |  |  | Public debt administration |  |  |  |  | - |  |  |  |  |  |  | Budget of RS* (The budget is unknown and will depend on the issuance volume, which has not yet been determined) |  |  |  |  |  |  |  |  |  |  |  |  |  | 2201-0004 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |
| 2.4.3 Issuance of green/sustainable government bonds on the domestic market |  | Q4 2028 |  |  |  |  | Public debt administration |  |  |  |  | - |  |  |  |  |  |  | Budget of RS* (The budget is unknown and will depend on the issuance volume, which has not yet been determined) |  |  |  |  |  |  |  |  |  |  |  |  |  | 2201-0004 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |
| 2.4.4 Improvement of reporting through the application of business intelligence tools within the existing information system (PDMS) |  | Q4 2028 |  |  |  |  | Public debt administration |  |  |  |  | - |  |  |  |  |  |  | Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | 15.000* |  |  |  |  |
| Measure 2.5: Strengthening the capacities of public procurement officials |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure |  | Link to program budget |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Donor funds |  | - |  |  |  |  |  |  |  |  |  | 2026: 3.120 |  |  |  |  |  |  |  |  |  |  |  | 2027: 3.120 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 3.120 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Public procurement office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) |  | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |
| Number of certified public procurement officials |  | Number |  |  |  |  |  |  |  |  |  | Annual report on public procurement |  |  |  |  |  |  | 5790 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5850 |  |  |  |  |  |  |  |  |  | 5950 |  |  |  |  |  |  |  |  |  | 6100 |  |  |  |  |
| Activity name: |  | Deadline for implementation of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  | Partners in the implementation of the activity |  |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  |
| 2.5.1 Trainings for exam preparation for public procurement officers |  | Q4 2028 continued |  |  |  |  | Public procurement office |  |  |  |  | EU/UNDP |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 960* |  |  |  |  |  |  |  |  |  | 960* |  |  |  |  |  |  |  |  |  | 960* |  |  |  |  |
| 2.5.2 Development of practical tools for public procurement officers for applying the Public Procurement Law and using the Public Procurement Portal |  | Q4 2028 continued |  |  |  |  | Public procurement office |  |  |  |  | NALED EU/UNDP |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.200* |  |  |  |  |  |  |  |  |  | 1.200* |  |  |  |  |  |  |  |  |  | 1.200* |  |  |  |  |
| 2.5.3 Trainings and workshops for public procurement officers on planning and market research |  | Q4 2028 continued |  |  |  |  | Public procurement office |  |  |  |  | EU/UNDP |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 480* |  |  |  |  |  |  |  |  |  | 480* |  |  |  |  |  |  |  |  |  | 480* |  |  |  |  |
| 2.5.4 Conducting annual training sessions and workshops for public procurement officials on preventing conflicts of interest and corruption |  | Q4 2028 |  |  |  |  | Public procurement office |  |  |  |  | EU/UNDP |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 480* |  |  |  |  |  |  |  |  |  | 480* |  |  |  |  |  |  |  |  |  | 480* |  |  |  |  |
| SPECIFIC OBJECTIVE III: IMPROVING BUDGET DISCIPLINE AND MORE TRANSPARENT USE OF PUBLIC FUNDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at a specific objective level (outcome indicator) |  |  | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Level of achieved progress within Negotiating Chapter 22 |  |  | - Early stage - Some level of preparation - Moderately prepared - Good level of preparation - Well advanced |  |  |  |  |  |  |  |  |  | Annual report |  |  |  | Moderately prepared |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  | Moderately prepared |  |  |  |  |  |  |  |  |  | Moderately prepared |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Good level of preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 3.1: Expansion of audit coverage and development of a new audit methodology under the competence of Governmental Audit Office of EU funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure |  |  | Link to program budget |  |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS and donor funds |  |  | 2301-0001 |  |  |  |  |  |  |  |  |  |  | 2026: 12.920 |  |  |  |  |  |  |  |  |  |  | 2027: 8.000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 8.000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Governmental Audit Office of EU funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2028 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) |  |  |  | Unit of measure |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |
| Number of developed methodological frameworks for audits |  |  |  | Number |  |  |  |  |  |  |  |  |  | Decision on adoption |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |
| Activity name: |  |  |  | Deadline for implementation of the activity |  |  |  | Institution responsible for implementation |  |  |  |  |  | Partners in the implementation of the activity |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  | 2028 |  |  |  |
| 3.1.1 Staffing the internal audit group of the General Secretariat and Government services by hiring internal auditors |  |  |  | Q4 2027 |  |  |  | Governmental Audit Office of EU funds |  |  |  |  |  | Human resources management service |  |  |  |  |  | Budget of RS |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2301-0001 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 8.000 |  |  |  |  |  |  |  |  |  | 8.000 |  |  |  |  |  |  |  |  | 8.000 |  |  |  |
| 3.1.2 Development of an audit methodological framework for IPARD III (measures 4 and 6) in accordance with EU requirements |  |  |  | Q4 2026 |  |  |  | Governmental Audit Office of EU funds |  |  |  |  |  |  |  |  |  |  |  | Donor funds - TAIEX |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  | - |  |  |  |
| 3.1.3 Development of a methodological framework for auditing the Reform and Growth Instrument |  |  |  | Q4 2026 |  |  |  | Governmental Audit Office of EU funds |  |  |  |  |  |  |  |  |  |  |  | Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2.520 |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  | - |  |  |  |
| 3.1.4 Development of capacities for control and audit of the Reform and Growth Instrument through targeted trainings |  |  |  | Q4 2026 |  |  |  | Governmental Audit Office of EU funds, EU, MoF, MEI, SAI. |  |  |  |  |  |  |  |  |  |  |  | Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2.400 |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  | - |  |  |  |
| Measure 3.2: Strengthening the system for more efficient and effective management of EU funds and enhancing the capacity of competent institutions in the area of protection of the EU interests |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure |  |  |  | Link to program budget |  |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS and donor funds |  |  |  | 0615-0001 2301-0014 |  |  |  |  |  |  |  |  |  |  | 2026: 10.122,48 |  |  |  |  |  |  |  |  |  |  | 2027: 26.244,97 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 20.244,97 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Department for EU funds management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) |  |  |  | Unit of measure |  |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |
| Percentage of confirmed irregularities identified during on-the-spot and administrative controls in relation to the total number of confirmed cases of irregularities |  |  |  | Percentage (%) |  |  |  |  |  |  |  |  |  |  | AFIS-IMS reporting system Annual reports on implementation of IPA programs |  |  |  |  |  | 85% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 85% |  |  |  |  |  |  |  |  |  | 85% |  |  |  |  |  |  |  |  | 85% |  |  |  |
| Activity name: |  |  |  | Deadline for implementation of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  |  | Partners in the implementation of the activity |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  | 2028 |  |  |  |
| 3.2.1 Coordination of the preparation of a plan for the implementation of continuous professional training related to management and oversight within the system for indirect management of European Union Instrument for Pre-accession Assistance funds |  |  |  | Q4 2028 |  |  |  |  | Ministry of Finance – Department for EU funds management |  |  |  |  |  | NAPA |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0615-0001 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |
| 3.2.2 Ensuring an adequate number of civil servants and enhancing the capacity of all participants in the process of managing European Union funds. |  |  |  | Q4 2028 |  |  |  |  | Ministry of Finance – Department for EU funds management |  |  |  |  |  | Human resources management service |  |  |  |  |  | Budget of RS |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2301-0014 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 10.122,48 |  |  |  |  |  |  |  |  |  | 20.244,97 |  |  |  |  |  |  |  | 20.244,97 |  |  |  |
| 3.2.3 Amendments to and supplementation of the relevant national legislation concerning the application of the Guidelines for Financial Corrections, and adoption of the Guidelines for Financial Corrections related to the use of EU funds. |  |  |  | Q2 2027 |  |  |  |  | Ministry of Finance – Department for EU funds management |  |  |  |  |  |  |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2301-0014 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |
| 3.2.4 Preparation and adoption of the Strategic Plan 2028–2030 to improve the work of national institutions relevant to the protection of the EU’s financial interests. |  |  |  | Q4 2027 |  |  |  |  | Ministry of Finance - AFCOS |  |  |  |  |  | AFCOS network |  |  |  |  |  | Budget of RS/Regular allocations Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | 1.000* |  |  |  |  |  |  |  | - |  |  |  |
| 3.2.5 Organization of a regional conference/seminar to exchange experiences in combating fraud. |  |  |  | Q4 2027 |  |  |  |  | Ministry of Finance - AFCOS |  |  |  |  |  | European anti-fraud office (OLAF) |  |  |  |  |  | Budget of RS/Regular allocations Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | 5.000* |  |  |  |  |  |  |  | - |  |  |  |
| Measure 3.3: Increasing the efficiency and effectiveness of inspection oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure |  |  |  |  | Link to program budget |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS and donor funds |  |  |  | 2301-0004 |  |  |  |  |  |  |  |  |  |  | 2026: - |  |  |  |  |  |  |  |  |  |  | 2027: 2.250 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 2.250 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Budget inspection department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) |  |  |  | Unit of measure |  |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  | Target value 2028 |  |  |  |
| Percentage of inspections conducted in response to complaints included in the annual inspection plan for the current year, relative to the number of complaints received within the jurisdiction of the Budget Inspection in the previous year. |  |  |  | Percentage (%) |  |  |  |  |  |  |  |  |  |  | Annual report on the work of the budget inspection |  |  |  |  |  | 47% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 48% |  |  |  |  |  |  |  |  |  | 50% |  |  |  |  |  |  |  | 52% |  |  |  |
| Activity name: |  |  |  | Deadline for implementation of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  |  | Partners in the implementation of the activity |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  | 2028 |  |  |  |
| 3.3.1 Adoption of a Guide for planning and oversight of the budget inspection (standards of work of the budget inspection) |  |  |  | Q4 2026 |  |  |  |  | Ministry of Finance, Budget inspection department |  |  |  |  |  | - |  |  |  |  |  | Direct donor support (GIZ) - (Public Finance Reform Project – Financing Agenda 2030) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |
| 3.3.2 Professional development of budget inspectors and other employees in the budget inspection through continuous education |  |  |  | Q4 2028 |  |  |  |  | Ministry of Finance, Budget inspection department |  |  |  |  |  | - |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2301-0004 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |
| 3.3.3 Ensuring the required number of employees – 66 |  |  |  | Q4 2028 |  |  |  |  | Ministry of Finance, Budget inspection department |  |  |  |  |  | - |  |  |  |  |  | Budget of RS |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2301-0004 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | 2.250 |  |  |  |  |  |  |  | 2.250 |  |  |  |
| SPECIFIC OBJECTIVE IV: IMPROVEMENT OF THE APPLICATION OF THE INTERNAL FINANCIAL CONTROL SYSTEM IN THE PUBLIC SECTOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at specific objective level (outcome indicator) |  |  |  | Unit of measure |  |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  | Target value 2028 |  |  |  |
| Level of progress identified in the area of Internal Financial Control in the EC progress report on the Republic of Serbia for the given year |  |  |  | - Early stage - Some level of preparation - Moderately prepared - Good level of preparation - Well advanced |  |  |  |  |  |  |  |  |  |  | EC report on Serbia for the given year (Chapter 32) |  |  |  |  |  | Moderately prepared |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Moderately prepared |  |  |  |  |  |  |  |  |  | Good level of preparation |  |  |  |  |  |  |  | Good level of preparation |  |  |  |
| Measure 4.1: Improvement of the internal financial control system in public sector institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure |  |  |  | Link to program budget |  |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS and donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026: 2.800 |  |  |  |  |  |  |  |  |  |  | 2027: 900 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 600 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Central harmonization unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) |  |  | Unit of measure |  |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  | Target value 2028 |  |  |  |
| Percentage of priority public sector bodies (PSBs) submitting reports on the state of the IFC system |  |  | Percentage (%) |  |  |  |  |  |  |  |  |  |  | Consolidated annual report |  |  |  |  |  |  | 86,78% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 90% |  |  |  |  |  |  |  |  |  | 92% |  |  |  |  |  |  |  | 95% |  |  |  |
| Percentage of priority PSBs that have prepared a risk register |  |  | Percentage (%) |  |  |  |  |  |  |  |  |  |  | Consolidated annual report |  |  |  |  |  |  | 72,19% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 77% |  |  |  |  |  |  |  |  |  | 82% |  |  |  |  |  |  |  | 87% |  |  |  |
| Activity name: |  |  | Deadline for implementation of the activity |  |  |  |  | Institution responsible for implementation |  |  |  |  |  | Partners in the implementation of the activity |  |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  | 2028 |  |  |  |
| 4.1.1 Improvement of risk management implementation through support to PSBs |  |  | Q4 2027 |  |  |  |  | CHU |  |  |  |  |  |  |  |  |  |  |  |  | Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.800 |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |
| 4.1.2 Enhancement of the annual IFC reporting questionnaire for the priority group of PSBs |  |  | Q4 2027 |  |  |  |  | CHU |  |  |  |  |  | - |  |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |
| 4.1.3 Development of an internal act model – a model for managing irregularities |  |  | Q4 2027 |  |  |  |  | CHU |  |  |  |  |  | Ministry of public administration and local self-government and Agency for prevention of corruption, MoF - AFCOS |  |  |  |  |  |  | Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | 300 |  |  |  |  |  |  |  | - |  |  |  |
| 4.1.4 Promotion of IFC – application of good practices in priority public sector bodies |  |  | Q4 2028 |  |  |  |  | CHU |  |  |  |  |  | State administration bodies |  |  |  |  |  |  | Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.000 |  |  |  |  |  |  |  |  |  | 600 |  |  |  |  |  |  |  | 600 |  |  |  |
| Measure 4.2. Enhanced internal audit function in the public sector in accordance with international standards and principles |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure |  |  | Link to program budget |  |  |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026: 17.550 |  |  |  |  |  |  |  |  |  |  |  | 2027: 5.200 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 5.200 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Central harmonization unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2028 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) |  |  | Unit of measure |  |  |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  | Target value 2028 |  |  |  |
| Percentage of priority public sector bodies (PSBs) that have an internal auditor employed in the organization (from those required by law to have an internal audit unit) |  |  | Percentage (%) |  |  |  |  |  |  |  |  |  |  |  | Consolidated annual report |  |  |  |  |  | 80,82% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 83% |  |  |  |  |  |  |  |  |  | 85% |  |  |  |  |  |  |  | 87% |  |  |  |
| Total number of improved materials in the area of internal financial control |  |  | Number |  |  |  |  |  |  |  |  |  |  |  | Materials published on the website |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 |  |  |  |  |  |  |  |  |  | 3 |  |  |  |  |  |  |  | 4 |  |  |  |
| Activity name: |  |  |  | Deadline for implementation of the activity |  |  |  |  |  | Institution responsible for implementation |  |  |  |  |  | Partners in the implementation of the activity |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ)) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  | 2028 |  |
| 4.2.1 Improvement of the regulatory framework and methodological materials (rulebooks and manuals) in accordance with new international standards |  |  |  | Q4 2028 |  |  |  |  |  | CHU |  |  |  |  |  |  |  |  |  |  |  | Donor funds UNDP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | 1.950 |  |  |  |  |  |  |  | 1.950 |  |  |
| 4.2.2 Enhancement of the certification process for obtaining the title of Chief Internal Auditor (CIA) in public sector bodies |  |  |  | Q4 2028 |  |  |  |  |  | CHU |  |  |  |  |  |  |  |  |  |  |  | Donor funds UNDP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | 1.950 |  |  |  |  |  |  |  | 1.950 |  |  |
| 4.2.3 Thematic workshops in the field of internal audit |  |  |  | Q4 2028 |  |  |  |  |  | CHU |  |  |  |  |  |  |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.300* |  |  |  |  |  |  |  |  |  | 1.300* |  |  |  |  |  |  |  | 1.300* |  |  |
| 4.2.4 Development of a model Charter, Strategic and Annual Plan based on the risk matrix for the audit universe, and conducting horizontal audits |  |  |  | Q4 2026 |  |  |  |  |  | Governmental Audit Office of EU funds |  |  |  |  |  | Ministry of Finance - CHU |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 16.250* |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |
| Measure 4.3: Improvement of IT systems to include modules for internal control and internal audit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure |  |  |  | Link to program budget |  |  |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026: 3.600 |  |  |  |  |  |  |  |  |  |  |  | 2027: 3.600 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 6.720 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Central harmonization unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) |  |  |  | Unit of measure |  |  |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  | Target value 2028 |  |  |
| Total number of established modules within the IT system |  |  |  | Number |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 |  |  |  |  |  |  |  |  |  | 3 |  |  |  |  |  |  |  | - |  |  |
| Activity name: |  |  |  | Deadline for implementation of the activity |  |  |  |  |  | Institution responsible for implementation |  |  |  |  |  | Partners in the implementation of the activity |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  | 2028 |  |
| 4.3.1 Improvement of the reporting application and development of software for internal audit |  |  |  | Q4 2028 |  |  |  |  |  | CHU |  |  |  |  |  |  |  |  |  |  |  | Budget of RS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3.600 |  |  |  |  |  |  |  |  |  | 3.600 |  |  |  |  |  |  |  | 6.720 |  |
| SPECIFIC OBJECTIVE V: IMPROVED ACCOUNTING IN THE PUBLIC SECTOR THROUGH APPLICATION OF INTERNATIONAL PUBLIC SECTOR ACCOUNTING STANDARDS (IPSAS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at specific objective level (outcome indicator) |  |  |  | Unit of measure |  |  |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  | Target value 2028 |  |  |
| Improved quality of financial statements in terms of the application of cash-based IPSAS, according to the SAI (State Audit Institution) report on the audit of the budget final account |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  | Annual report of SAI or SAI report on the audit of the budget final account of the Republic of Serbia |  |  |  |  |  | No |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  |  |  |  | Yes |  |  |
| Measure 5.1: Application of IPSAS standards on a cash basis for all budget users |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure |  |  |  | Link to program budget |  |  |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS |  |  |  | 2301-5002 2301-5007 2301-0008 |  |  |  |  |  |  |  |  |  |  |  | 2026: 1.500 |  |  |  |  |  |  |  |  |  |  |  | 2027: - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Treasury administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) |  |  |  | Unit of measure |  |  |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  | Target value 2028 |  |  |
| Draft financial statement prepared in accordance with IPSAS on a cash basis |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  | SAI report |  |  |  |  |  | No |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  |  |  |  | Yes |  |  |
| Activity name: |  |  |  | Deadline for implementation of the activity |  |  |  |  |  | Institution responsible for implementation |  |  |  |  |  | Partners in the implementation of the activity |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  | 2028 |  |
| 5.1.1 Preparation and submission of financial statements in accordance with IPSAS on a cash basis |  |  |  | Q2 2026 |  |  |  |  |  | Treasury administration |  |  |  |  |  | Ministry of Finance |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2301-5002 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |
| 5.1.2 Preparation of notes and additional explanations accompanying the financial statements in accordance with IPSAS on a cash basis |  |  |  | Q2 2026 |  |  |  |  |  | Treasury administration |  |  |  |  |  | Ministry of Finance |  |  |  |  |  | Budget of RS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2301-5007 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.500 |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |
| 5.1.3 Conducting trainings to improve the professional competence of public sector accountants in accordance with the Professional Training Program for bookkeeping, preparation, and presentation of financial statements in accordance with IPSAS on a cash basis |  |  |  | Q4 2028 |  |  |  |  |  | Treasury administration |  |  |  |  |  | NAPA |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2301-0008 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |
| Measure 5.2: Further improvement of budget accounting according to the Public sector accounting improvement plan in line with IPSAS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure |  |  |  | Link to program budget |  |  |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS and donor funds |  |  |  | 2301-5007 |  |  |  |  |  |  |  |  |  |  |  | 2026: - |  |  |  |  |  |  |  |  |  |  |  | 2027: 2.800 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 2800 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Treasury administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) |  |  |  | Unit of measure |  |  |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  | Target value 2028 |  |  |
| Drafted Public sector accounting improvement plan in accordance with IPSAS |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  | Treasury administration website |  |  |  |  |  | No |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | Yes |  |  |
| Activity name: |  |  |  | Deadline for implementation of the activity |  |  |  |  |  | Institution responsible for implementation |  |  |  |  |  | Partners in the implementation of the activity |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  | 2028 |  |
| 5.2.1 Development of the Public Sector Accounting Improvement Plan in line with IPSAS, including a plan for improving IT systems. |  |  |  | Q4 2028 |  |  |  |  |  | Treasury administration |  |  |  |  |  | Ministry of Finance |  |  |  |  |  | Budget of RS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2301-5007 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | 2.000 |  |  |  |  |  |  |  | 2.000 |  |
| 5.2.2 Ensuring the translation of the International Public Sector Accounting Standards (IPSAS) |  |  |  | Q4 2028 |  |  |  |  |  | Treasury administration |  |  |  |  |  | Ministry of Finance, Serbian Association of Accountants and Auditors |  |  |  |  |  | Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |
| 5.2.3 Enhancement of the capacities of employees in the Treasury Administration for IPSAS implementation, including study visits to countries with successful IPSAS adoption. |  |  |  | Q4 2028 |  |  |  |  |  | Treasury administration |  |  |  |  |  | Ministry of Finance |  |  |  |  |  | Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | 800* |  |  |  |  |  |  |  | 800* |  |
| SPECIFIC OBJECTIVE VI: EXTERNAL OVERSIGHT OF PUBLIC FINANCES ENHANCED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at specific objective level (outcome indicator) |  |  |  | Unit of measure |  |  |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  | Target value 2028 |  |  |
| Percentage of audited public fund beneficiaries with deficiencies in the internal control system |  |  |  | Percentage (%) |  |  |  |  |  |  |  |  |  |  |  | Report on the works of SAI |  |  |  |  |  | 85% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 84% |  |  |  |  |  |  |  |  |  | 83% |  |  |  |  |  |  |  | 82% |  |  |
| Measure 6.1: Strengthening the efficiency and impact of external audit through the integration of modern technologies, improvement of methodology and communication with stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure |  |  |  | Link to program budget |  |  |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS and donor funds |  |  |  | 2304-0001 |  |  |  |  |  |  |  |  |  |  |  | 2026: 21.990 |  |  |  |  |  |  |  |  |  |  |  | 2027: 21.990 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028:21.990 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: State audit institution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) |  |  |  | Unit of measure |  |  |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  | Target value 2028 |  |  |
| Percentage of DRI recommendations implemented within 2 years of the publication of the report |  |  |  | Percentage (%) |  |  |  |  |  |  |  |  |  |  |  | Internal reports on tracking the implementation of SAI recommendations |  |  |  |  |  | 78% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 80% |  |  |  |  |  |  |  |  |  | 81% |  |  |  |  |  |  |  | 82% |  |  |
| Activity name: |  |  |  | Deadline for implementation of the activity |  |  |  |  |  | Institution responsible for implementation |  |  |  |  |  | Partners in the implementation of the activity |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  | 2028 |  |
| 6.1.1 Development and adoption of guidelines for performance and compliance audits, along with regular training for auditors in performance auditing |  |  |  | Q4 2026 |  |  |  |  |  | ДРИ |  |  |  |  |  | SAI – Audit methodology and development department; Audit department |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2304-0001 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |
| 6.1.2 Development of a methodology for selecting and conducting follow-up audits to monitor the implementation of recommendations. |  |  |  | Q4 2027 |  |  |  |  |  | SAI |  |  |  |  |  | SAI – Audit services |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2304-0001 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |
| 6.1.3 Creation of an internal database of good practices and typical findings |  |  |  | Q2 2027 |  |  |  |  |  | SAI |  |  |  |  |  | SAI – Audit methodology and development department; ICT department |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2304-0001 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |
| 6.1.4 Integration of modern technologies in auditing through development and implementation of automated audit tests, piloting artificial intelligence in auditing and introduction of digital platforms for collaboration and data sharing within audit teams |  |  |  | Q4 2028 |  |  |  |  |  | SAI |  |  |  |  |  | SAI – ICT department; External providers; IDI/EUROSAI |  |  |  |  |  | Budget of RS/Regular allocations Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2304-0001 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 21.990 |  |  |  |  |  |  |  |  |  | 21.990 |  |  |  |  |  |  |  | 21.990 |  |
| Measure 6.2: Ensuring effective parliamentary oversight over public finances |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funding for the measure |  |  |  | Link to program budget |  |  |  |  |  |  |  |  |  |  |  | Total estimated financial resources in 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget of RS and donor funds |  |  |  | 2101-0001 2101-0003 |  |  |  |  |  |  |  |  |  |  |  | 2026: 2.000 |  |  |  |  |  |  |  |  |  |  |  | 2027: 2.000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2028: 2.000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: National assembly – Committee on Finance, state budget and control of public spending |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (output indicator) |  |  |  | Unit of measure |  |  |  |  |  |  |  |  |  |  |  | Source of verification |  |  |  |  |  | Initial value |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Base year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  | Target value 2028 |  |  |
| Percentage of SAI reports reviewed in the National Assembly |  |  |  | Percentage (%) |  |  |  |  |  |  |  |  |  |  |  | Reports and minutes of the National assembly Finance committee |  |  |  |  |  | 50% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 55% |  |  |  |  |  |  |  |  |  | 60% |  |  |  |  |  |  |  | 65% |  |  |
| Number of Committee meetings/sessions held for reviewing recommendations for amendments to laws in the presence of DRI and the Ministry of Finance, annually |  |  |  | Number |  |  |  |  |  |  |  |  |  |  |  | Minutes of the session/meeting |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | 1 |  |  |
| Activity name: |  |  |  | Deadline for implementation of the activity |  |  |  |  |  | Institution responsible for implementation |  |  |  |  |  | Partners in the implementation of the activity |  |  |  |  |  | Financial resources in thousands RSD (000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Link to program budget (PR-PA/PJ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  | 2028 |  |
| 6.2.1 Holding Committee and Subcommittee sessions for reviewing SAI audit reports, outside the National Assembly premises |  |  |  | Q4 2028 |  |  |  |  |  | National assembly – Committee on Finance, state budget and control of public spending – Subcommittee for reviewing SAI audit reports |  |  |  |  |  | SAI |  |  |  |  |  | Budget of RS/Regular allocations Donor funds* |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2101-0001 2101-0003 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2.000 |  |  |  |  |  |  |  |  |  | 2.000 |  |  |  |  |  |  |  | 2.000 |  |  |
| 6.2.2 Holding joint sessions of the competent parliamentary committees to review performance audit reports |  |  |  | Q4 2028 |  |  |  |  |  | National assembly – Committee on Finance, state budget and control of public spending – Subcommittee for reviewing SAI audit reports and other competent committees |  |  |  |  |  | SAI |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2101-0001 2101-0003 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |
| 6.2.3 Organizing public hearings regarding the presentation of the Draft Budget Law and the Draft Law on the Budget Final Account |  |  |  | Q4 2028 |  |  |  |  |  | National assembly – Committee on Finance, state budget and control of public spending |  |  |  |  |  | Ministry of Finance, State audit institution, Fiscal council and National bank of Serbia |  |  |  |  |  | Budget of RS/Regular allocations |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2101-0001 2101-0003 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |

# ANNEX 1 – SEQUENCE OF IMPLEMENTATION OF THE Pfmrp ACTION PLAN ACTIVITIES FOR THE PERIOD 2026–2028

| MEASURES/ACTIVITIES | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| Measure 1.1: Improvement of the Programme Budget and Medium-term Expenditure Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 Introduction of program budget in healthcare institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 Development of methodologies and manuals for the preparation of program budgets and reporting on program performance at all levels of government |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.3 Improvement of modules for monitoring and evaluation of program performance and preparation of a consolidated performance report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.4 Improvement of the system and development models for more credible expenditure projections and increased budget transparency |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 1.2: Strengthening institutional capacities and improving the methodological framework for green budgeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 Organization of workshops for budget analysts to strengthen capacities for green budgeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 Expansion of the scope of the green budgeting methodology in terms of types of expenditures and levels of government |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 Strengthening the capacities of the green budgeting working group through training and workshops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.4 Study visit – example of good practice in green budgeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 1.3: Harmonization of the budget process in the Republic of Serbia with the budget process in the European Union |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 Analyses of the budget preparation process in the Republic of Serbia and its alignment with the budget process in EU countries |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 Development of guidelines for harmonizing the budget process with EU standards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.3 Strengthening the capacities of budget analysts for budget preparation in accordance with EU regulations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 1.4: Improvement of the environment for efficient management of capital projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.1 Amendments and supplements to the legal framework in accordance with identified weaknesses in practical implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.2 Improvement and standardization of public reports on the status of capital projects monitored in accordance with the methodology |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.3 Familiarization of the officials from Department for Capital Projects with good international practices related to planning, monitoring, and reporting in the field of public investments through a study visit and the organization of a workshop for employees of the Department for Capital Projects and other departments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.4 Preparation of a manual on the methodology in the field of capital projects (design, preparation for printing, proofreading, consulting support for content) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 1.5: Strengthening the capacities of the Section for fiscal risk monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.1 Improvement and standardization of reporting on fiscal risks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.2 Revision of the methodology for monitoring fiscal risks related to the operations of state-owned enterprises and local self-governments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.3 Development of methodology for linking budget reserves with quantified risk indicators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.4 Development of a methodology for monitoring fiscal risks from climate change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 1.6: Establishment of a system for coordination and management of EU own resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.1 Establishment of operational and procedural links between institutions with the aim of improving coordination and data exchange in accordance with the obligations of Chapter 33 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.2 Development and improvement of systems, processes and procedures in organizational and informational, i.e. technical and technological terms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.3 Establishment and development of administrative capacities through the creation of appropriate organizational units, recruitment, and training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 1.7: Improvement of medium-term planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.1 Providing systematic mentoring support for the preparation of medium-term plans of entities subject to medium-term planning at the national level, in order to achieve better alignment with the entities’ annual budgets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.2 Establishment of a network of medium-term planning coordinators to improve the alignment of public policy planning with the medium-term expenditure framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 2.1: Efficient collection of budget revenues under the competence of the Tax Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 Implementation of a ready-made commercial solution for an Integrated Tax Management Information System (COTS-ITMS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 Improved educational function within the Tax Administration of the Republic of Serbia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 Further harmonization of national legislation and development of a roadmap relevant for supporting the implementation of international information exchange systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4 Enhanced strategic competencies for human resource management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.5 Introduction of a preliminary VAT return through the upgrade of the e-Invoice system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.6 Improvement of the e-Delivery Note system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.7 Further enhancement of the eExcise system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.8 Harmonization of selected tax laws of the Republic of Serbia (VAT, Personal Income Tax, Corporate Income Tax, Excise Duties, and the Law on Tax Procedure and Tax Administration) with the EU acquis communautaire (Chapter 16 – Taxation) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.9 Drafting of accompanying by-laws |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.10 Preparation of a change management plan and capacity building for the business community regarding the practical implementation of fiscal regulations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.11. Establishment of a central factoring registry |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 2.2: Reduction of administrative burden and improvement of efficiency in providing electronic services under the competence of Tobacco administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 Preparation, publication, and implementation of video trainings and guidelines to support business entities in using the portal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 Improvement of the efficiency of processing reports submitted through the portal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measures 2.3: Strengthening the administrative capacities of the Customs administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 Upgrade of the NCTS transit procedure application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 Improvement of capacities for effective post-clearance audits, determination of customs value, preferential origin, and classification of goods |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.3 Modernization of the customs laboratory |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.4 Implementation of import and export automated systems (AIS-AES) and control system (CDS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.5 Development of a system for collection of budget revenues, collection monitoring, and integration with automated systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.6 Implementation of software for integrated tariff management (ITMS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.7 Procurement and implementation of a data warehouse for storing customs data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 2.4: Efficient public debt management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.1 Expansion of reporting scope (units) through development and implementation of an Information System for submission of financial reports |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.2 Issuance of green/sustainable Eurobonds on the international market |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.3 Issuance of green/sustainable government bonds on the domestic market |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.4 Improvement of reporting through the application of business intelligence tools within the existing information system (PDMS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 2.5: Strengthening the capacities of public procurement officials |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.1 Trainings for exam preparation for public procurement officers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.2 Development of practical tools for public procurement officers for applying the Public Procurement Law and using the Public Procurement Portal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.3 Trainings and workshops for public procurement officers on planning and market research |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.4 Conducting annual training sessions and workshops for public procurement officials on preventing conflicts of interest and corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 3.1: Expansion of audit coverage and development of a new audit methodology under the competence of Governmental Audit Office of EU funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 Staffing the internal audit group of the General Secretariat and Government services by hiring internal auditors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 Development of an audit methodological framework for IPARD III (measures 4 and 6) in accordance with EU requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.3 Development of a methodological framework for auditing the Reform and Growth Instrument |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.4 Development of capacities for control and audit of the Reform and Growth Instrument through targeted trainings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 3.2: Strengthening the system for more efficient and effective management of EU funds and enhancing the capacity of competent institutions in the area of protection of the EU interests |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 Coordination of the preparation of a plan for the implementation of continuous professional training related to management and oversight within the system for indirect management of European Union Instrument for Pre-accession Assistance funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.2 Ensuring an adequate number of civil servants and enhancing the capacity of all participants in the process of managing European Union funds. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.3 Amendments to and supplementation of the relevant national legislation concerning the application of the Guidelines for Financial Corrections, and adoption of the Guidelines for Financial Corrections related to the use of EU funds. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.4 Preparation and adoption of the Strategic Plan 2028–2030 to improve the work of national institutions relevant to the protection of the EU’s financial interests. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.5 Organization of a regional conference/seminar to exchange experiences in combating fraud. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 3.3: Increasing the efficiency and effectiveness of inspection oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 Adoption of a Guide for planning and oversight of the budget inspection (standards of work of the budget inspection) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.2 Professional development of budget inspectors and other employees in the budget inspection through continuous education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.3 Ensuring the required number of employees – 66 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 4.1: Improvement of the internal financial control system in public sector institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1 Improvement of risk management implementation through support to PSBs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.2 Enhancement of the annual IFC reporting questionnaire for the priority group of PSBs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.3 Development of an internal act model – a model for managing irregularities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.4 Promotion of IFC – application of good practices in priority public sector bodies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 4.2. Enhanced internal audit function in the public sector in accordance with international standards and principles |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2.1 Improvement of the regulatory framework and methodological materials (rulebooks and manuals) in accordance with new international standards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2.2 Enhancement of the certification process for obtaining the title of Chief Internal Auditor (CIA) in public sector bodies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2.3 Thematic workshops in the field of internal audit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2.4 Development of a model Charter, Strategic and Annual Plan based on the risk matrix for the audit universe, and conducting horizontal audits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 4.3: Improvement of IT systems to include modules for internal control and internal audit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3.1 Improvement of the reporting application and development of software for internal audit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 5.1: Application of IPSAS standards on a cash basis for all budget users |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1.1 Preparation and submission of financial statements in accordance with IPSAS on a cash basis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1.2 Preparation of notes and additional explanations accompanying the financial statements in accordance with IPSAS on a cash basis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1.3 Conducting trainings to improve the professional competence of public sector accountants in accordance with the Professional Training Program for bookkeeping, preparation, and presentation of financial statements in accordance with IPSAS on a cash basis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 5.2: Further improvement of budget accounting according to the Public sector accounting improvement plan in line with IPSAS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2.1 Development of the Public Sector Accounting Improvement Plan in line with IPSAS, including a plan for improving IT systems. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2.2 Ensuring the translation of the International Public Sector Accounting Standards (IPSAS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2.3 Enhancement of the capacities of employees in the Treasury Administration for IPSAS implementation, including study visits to countries with successful IPSAS adoption. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 6.1: Strengthening the efficiency and impact of external audit through the integration of modern technologies, improvement of methodology and communication with stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1.1 Development and adoption of guidelines for performance and compliance audits, along with regular training for auditors in performance auditing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1.2 Development of a methodology for selecting and conducting follow-up audits to monitor the implementation of recommendations. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1.3 Creation of an internal database of good practices and typical findings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1.4 Integration of modern technologies in auditing through development and implementation of automated audit tests, piloting artificial intelligence in auditing and introduction of digital platforms for collaboration and data sharing within audit teams |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 6.2: Ensuring effective parliamentary oversight over public finances |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.2.1 Holding Committee and Subcommittee sessions for reviewing SAI audit reports, outside the National Assembly premises |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.2.2 Holding joint sessions of the competent parliamentary committees to review performance audit reports |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.2.3 Organizing public hearings regarding the presentation of the Draft Budget Law and the Draft Law on the Budget Final Account |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# ANNEX 2: INDICATOR PROFILES FOR IMPACTS, OUTCOMES AND OUTPUTS

General objective indicator

| Indicator name | Real GDP growth |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | General objective: Achieving a sustainable budget and maintaining public debt at a stable level relative to GDP through strengthened financial management and control, enhanced audit processes, and closer alignment of budget planning with Government policies. |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Outcome indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | Revised Fiscal Strategy - https://www.mfin.gov.rs/dokumenti2/fiskalna-strategija ; Economic Reform Program - https://www.mfin.gov.rs/dokumenti2/program-ekonomskih-reformi-erp |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance |  |  |  |  |  |
| Frequency | Quarterly and annual. A preliminary estimate of the quarterly indicator value is published during the current quarter for the preceding quarter. A preliminary estimate of the annual indicator value is published in October of the current year for the preceding year, while the final estimate of the annual indicator value is published in October of the current year for the year two years prior. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | Real GDP growth is calculated as the rate of change in Gross Domestic Product (GDP) at constant prices (previous year's prices) and using chain-linked volume measures. It is intended to capture real changes in the dynamics and structure of GDP, independently of price effects. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  | Initial |  |
|  | 2021. | 2022. | 2023. |  | 2024. |  |
|  | 7,9% | 2,7% | 3,7% |  | 3,9% |  |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 3% | 5% | 3,5% |  |  |  |
| Performance assessment: | Deviation of the actual real GDP growth rate from the target real GDP growth rate by no more than 0.8 percentage points. |  |  |  |  |  |

| Indicator name | General government debt level in GDP |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding General Objective, Specific Objective or Measure | General objective: Achieving a sustainable budget and maintaining public debt at a stable level relative to GDP through strengthened financial management and control, enhanced audit processes, and improved alignment of budget planning with Government policies. |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Outcome indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Lower value is better |  |  |
| Data source | Revised Fiscal strategy (plan) and Public Debt Administration (execution) https://mfin.gov.rs/dokumenti2/fiskalna-strategija https://javnidug.gov.rs/rsc |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance |  |  |  |  |  |
| Frequency | The quarterly indicator value is published in the current quarter for the preceding quarter. The level of general government debt as of 31 December of the current year is published by the Public Debt Administration in its monthly and quarterly reports |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The share of general government debt in GDP is calculated as the ratio of the nominal value of general government debt to the nominal value of Gross Domestic Product (GDP), expressed as a percentage. Under the Public Debt Law, general government debt comprises the direct debt of the general government sector and government-issued guarantees (indirect debt), owed to both domestic and foreign creditors. General government debt may also be calculated in accordance with the EU methodology, i.e. the Maastricht definition of government debt. The Public Debt Administration calculates and publishes data on the ratio of general government debt to GDP in parallel, based on both the EU (Maastricht) definition and the definition set out in the Budget System Law. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  | Initial value |  |
|  | 2021. | 2022. | 2023. |  | 2024. |  |
|  | 54,5% | 52,9% | 48,4% |  | 46,9% |  |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 44,5% | 44,3% | 44,1% |  |  |  |
| Performance assessment: | Deviation of the actual general government debt-to-GDP ratio from the target ratio by no more than 2 percentage points. |  |  |  |  |  |

Indicator at specific objective level 1

| Indicator name | General Government deficit up to 3% of GDP |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Specific objective 1: Capacity for budget planning and public investment management improved |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Outcome indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Lower value is better |  |  |
| Data source | Revised Fiscal Strategy and macroeconomic and fiscal data (Ministry of Finance website) - https://www.mfin.gov.rs/dokumenti2/fiskalna-strategija https://www.mfin.gov.rs/dokumenti2/makroekonomski-podaci |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance, Budget department |  |  |  |  |  |
| Frequency | Actual data for the preceding year are published at the beginning of February. Planned values are presented in the Revised Fiscal Strategy for the year to which they relate |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator presents the general government deficit for each individual year and is published in the Revised Fiscal Strategy, which, in accordance with the budget calendar and the Budget System Law, is adopted by 15 October. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  | Initial value |  |
|  | 2021. | 2022. | 2023. |  | 2024. |  |
|  | 3,9% | 3% | 2,1% |  | 2% |  |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 3% | 3% | 2,5% |  |  |  |
| Performance assessment: | Deviation is not permitted. |  |  |  |  |  |

Indicator at specific objective level 2

| Indicator name | Actual revenues and expenditures of the state sector budget on an annual basis are within 5% of those projected in the fiscal strategy |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Specific objective 2: Efficient collection and management of budget funds |  |  |  |  |  |
| Indicator type | Qualitative |  |  | Outcome indicator |  |  |
| Unit of measure and nature | Percentage (%) |  |  | Improved planning and management of budget funds. |  |  |
| Data source | Revised Fiscal Strategy and macroeconomic and fiscal data (Ministry of Finance website) - https://www.mfin.gov.rs/dokumenti2/makroekonomski-podaci and https://www.mfin.gov.rs/dokumenti2/fiskalna-strategija |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Macroeconomic and fiscal projections and analyses department |  |  |  |  |  |
| Frequency | Once a year, in February for previous year. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | This indicator monitors the fiscal projections of actual revenues and expenditures presented in the Revised Fiscal Strategy, thereby measuring and supporting improvements in public revenue and expenditure planning, as well as the credibility of fiscal projections. Given the differences that may arise between actual revenue and expenditure outturns and the corresponding projections set out in the Revised Fiscal Strategy, it is envisaged that actual revenues and expenditures for the period 2026–2030 will remain within a deviation range of ±5% from the projected amounts contained in the Revised Fiscal Strategy adopted on an annual basis. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | 5% | 5% | 5% |  | 5% | 5% |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 5% | 5% | 5% |  |  |  |
| Performance assessment: | Deviation is not permitted. |  |  |  |  |  |

Indicator at specific objective level 3

| Indicator name | Level of achieved progress within Negotiating Chapter 22 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Specific objective 3: Improving budget discipline and more transparent use of public funds |  |  |  |  |  |
| Indicator type | Qualitative |  |  | Outcome indicator |  |  |
| Unit of measure and nature | European Commission assessment using a rating scale |  |  | Descriptive indicator |  |  |
| Data source | European Commission annual report |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Department for EU funds management |  |  |  |  |  |
| Frequency | Annually, in the fourth quarter of the current year, for the year in which it is published. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | This indicator tracks progress within the negotiation process under Chapter 22 and is measured on the basis of the European Commission’s annual report on the progress of the Republic of Serbia in the EU integration process. Rating scale: - Early stage - Some level of preparation - Moderately prepared - Good level of preparation - Well advanced |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | Moderately prepared | Moderately prepared | Moderately prepared |  | Moderately prepared | Moderately prepared |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | Moderately prepared | Moderately prepared | Good level of preparation |  |  |  |
| Процена успешности: | Deviation is not permitted. |  |  |  |  |  |

Indicator at specific objective level 4

| Indicator name | Level of progress identified in the area of Internal Financial Control in the EC progress report on the Republic of Serbia for the given year |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Specific objective 4: Improvement of the application of the internal financial control system in the public sector |  |  |  |  |  |
| Indicator type | Qualitative |  |  | Outcome indicator |  |  |
| Unit of measure and nature | European Commission assessment using a rating scale |  |  | Descriptive indicator |  |  |
| Data source | European Commission annual report (chapter 32) |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Central Harmonization Unit |  |  |  |  |  |
| Frequency | Annually, in the fourth quarter of the current year, for the reporting year |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The selected indicator is external and qualitative in nature, and is based on the European Commission’s assessment using the “General level of preparedness” rating scale. Rating scale: - Early stage - Some level of preparation - Moderately prepared - Good level of preparation - Well advanced |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | 3 | 3 | 3 |  | 3 | 3 |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 3 | 4 | 4 |  | 4 | 4 |
| Performance assessment: | The ultimate objective for 2030 is for the European Commission to assess that Negotiation Chapter 32 – Financial Control has achieved a good level of preparedness and that the closing benchmarks have been met. No deviation is acceptable. |  |  |  |  |  |

Indicator at specific objective level 5

| Indicator name | Improved quality of financial statements in terms of the application of cash-based IPSAS, according to the SAI (State Audit Institution) report on the audit of the budget final account |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Specific objective 5: Improved accounting in the public sector through application of International public sector accounting standards (IPSAS) |  |  |  |  |  |  |
| Indicator type | Qualitative |  |  |  | Outcome indicator |  |  |
| Unit of measure and nature | Yes/No |  |  |  | Yes is best value |  |  |
| Data source | Annual report of SAI or SAI report on the audit of the budget final account of the Republic of Serbia - https://www.dri.rs/izvestaji |  |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Treasury Administration |  |  |  |  |  |  |
| Frequency | Annually, in the current year for the previous year. |  |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | This indicator measures the quality of financial reporting in terms of compliance with cash-basis IPSAS. |  |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  |  | Initial value |
|  | 2021. |  | 2022. | 2023. |  | 2024. | 2025. |
|  |  |  |  |  |  |  | No |
| Data on target value | 2026. | 2027. |  | 2028. |  | 2029. | 2030. |
|  | Yes | Yes |  | Yes |  |  |  |
| Performance assessment: | Deviation is not permitted. |  |  |  |  |  |  |

Indicator at specific objective level 6

| Indicator name | Percentage of audited public fund beneficiaries with deficiencies in the internal control system |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Specific objective 6: External oversight of public finances enhanced |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Outcome indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Lower value is better |  |  |
| Data source | Report on the works of SAI - Годишњи извештаји о раду |  |  |  |  |  |
| Name of the entity responsible for data collection | State Audit Institution |  |  |  |  |  |
| Frequency | Annually, in the current year for the previous year. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator is calculated at the end of the current year as the share of audit entities—budget beneficiaries—within the total population of audited entities, in which findings related to internal control systems have been identified. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022 | 2023. |  | 2024. | 2025. |
|  | 85% | 85% | 86% |  | 85% | 85% |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 84% | 83% | 82% |  |  |  |
| Performance assessment: | Permissible deviation of up to 1% from the target value. |  |  |  |  |  |

INDICATORS AT MEASURE LEVEL

Indicator at measure level 1.1

| Indicator name | Percentage of healthcare institutions applying the program budget |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 1.1 - Improvement of the Programme Budget and Medium-term Expenditure Framework |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | Ministry of Finance internal report |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Budget department |  |  |  |  |  |
| Frequency | Annually, in the first quarter of the current year for the previous year. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator refers to the percentage of health institutions that have prepared their financial plans in accordance with the methodology for programme-based budgeting. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | / | / | / |  | / | 0 |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | / | 70% | 100% |  |  |  |
| Performance assessment: | A deviation of up to 10% is allowed. |  |  |  |  |  |

Indicator at measure level 1.2

| Indicator name | Coverage of the application of the green budgeting methodology across all levels of government |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 1.2 - Strengthening institutional capacities and improving the methodological framework for green budgeting |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | Ministry of Finance internal report |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Budget department |  |  |  |  |  |
| Frequency | Annually, in the first quarter of the current year for the previous year. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator refers to levels of government that have applied the methodology for tagging green projects in the budget preparation process. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | / | / | / |  | / | 50% |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 50% | 100% | 100% |  |  |  |
| Performance assessment: | A deviation of up to 10% is allowed. |  |  |  |  |  |

Indicator at measure level 1.3

| Indicator name | Percentage of trained budget analysts in the Ministry of Finance |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 1.3 - Harmonization of the budget process in the Republic of Serbia with the budget process in the European Union |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | Ministry of Finance internal report |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Budget department |  |  |  |  |  |
| Frequency | Annually, in the first quarter of the current year for the previous year. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator refers to the percentage of budget analysts who have completed training on budget preparation in line with the European Union budget process. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | / | / | / |  | / | 0 |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 80% | 100% | / |  |  |  |
| Performance assessment: | A deviation of up to 10% is allowed. |  |  |  |  |  |

Indicator at measure level 1.4

| Indicator name | Percentage of capital projects included in the budget, subject to assessment and evaluated in accordance with the methodology governing capital projects |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 1.4 - Improvement of the environment for efficient management of capital projects |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | Budget law/Commission for Capital Investments - https://mfin.gov.rs/propisi/zakoni/1 |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Department for capital projects |  |  |  |  |  |
| Frequency | Annually, after the adoption of Budget law |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator refers to capital projects that have passed the preparation phase in accordance with the Decree on Capital Projects and are included in the budget of the Republic of Serbia, but have not been designated as projects of special importance for the Republic of Serbia (where line ministries act as authorised proposers). |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | / | / | / |  | 40% | 60% |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 70% | 80% | 90% |  |  |  |
| Performance assessment: | A deviation of up to 5% is allowed. |  |  |  |  |  |

Indicator at measure level 1.5

| Indicator name | Published report on fiscal risks |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 1.5 - Strengthening the capacities of the Section for fiscal risk monitoring |  |  |  |  |  |
| Indicator type | Qualitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Published/Not published |  |  | Published is better value |  |  |
| Data source | Ministry of Finance website - https://www.mfin.gov.rs/ |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Budget department, Section for fiscal risk monitoring |  |  |  |  |  |
| Frequency | Annually |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator measures whether the Fiscal Risks Report has been prepared and publicly disclosed. Verification is carried out via the website of the Ministry of Finance. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | / | / | / |  | / | 0 |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | Published | Published | Published |  |  |  |
| Performance assessment: | Deviation is not permitted. |  |  |  |  |  |

| Indicator name | Amendments and additions of the Unified Methodology for Monitoring Fiscal Risks in the Republic of Serbia |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 1.5 - Strengthening the capacities of the Section for fiscal risk monitoring |  |  |  |  |  |
| Indicator type | Qualitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Adopted/Not adopted |  |  | Adopted is better value. |  |  |
| Data source | Official gazette of the Republic of Serbia |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Budget department, Section for fiscal risk monitoring |  |  |  |  |  |
| Frequency | As needed (once in the year of adoption) |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator measures whether the methodology has been revised and formally adopted. Verification is carried out through publication in the Official Gazette of the Republic of Serbia. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | / | / | / |  | / | 0 |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | / | / | Adopted |  |  |  |
| Performance assessment: | Deviation is not permitted. |  |  |  |  |  |

Indicator at measure level 1.6

| Indicator name | Level of progress within Negotiation chapter 33 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 1.6 - Establishment of a system for coordination and management of EU own resources |  |  |  |  |  |
| Indicator type | Qualitative |  |  | Output indicator |  |  |
| Unit of measure and nature | No progress achieved Limited Progress Some progress |  |  | Descriptive indicator |  |  |
| Data source | European Commission’s annual report on Serbia |  |  |  |  |  |
| Name of the entity responsible for data collection | The European Commission, based on submissions from the Ministry of Finance. |  |  |  |  |  |
| Frequency | Annually, in November for the current year. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator measures progress under Negotiation Chapter 33 – Financial and Budgetary Provisions. - No progress achieved - Limited progress - Some progress |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | Some progress | Limited progress | Limited progress |  | No progress achieved | No progress achieved |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | Limited progress | Some progress | Some progress |  |  |  |
| Performance assessment: | Deviation is not permitted. |  |  |  |  |  |

Indicator at measure level 1.7

| Indicator name | Number of adopted and published medium-term plans of entities obliged to conduct medium-term planning at the republic level |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 1.7 - Improvement of medium-term planning |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Number |  |  | Higher value is better |  |  |
| Data source | Websites of entities obliged to conduct medium-term planning |  |  |  |  |  |
| Name of the entity responsible for data collection | Public Policy Secretariat |  |  |  |  |  |
| Frequency | The indicator is published once a year, in the current year for the previous year. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator tracks the number of adopted and published medium-term plans of medium-term planning entities at the national level in a given year. Medium-term plans are published on the websites of the respective planning entities, while verification of their adoption is provided by the signature of the head of the planning entity. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025 |
|  | 7 | 22 | 26 |  | 28 | 29 |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 30 | 32 | 34 |  | 35 | 35 |
| Performance assessment: | Deviation is not permitted. |  |  |  |  |  |

| Indicator name | Percentage of published reports on the implementation of medium-term plans in relation to the total number of published medium-term plans valid for the year being reported on |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 1.7 - Improvement of medium-term planning |  |  |  |  |  |
| Indicator type | Quantitative |  | Output indicator |  |  |  |
| Unit of measure and nature | Percentage |  | Higher value is better |  |  |  |
| Data source | Websites of entities obliged to conduct medium-term planning |  |  |  |  |  |
| Name of the entity responsible for data collection | Public Policy Secretariat |  |  |  |  |  |
| Frequency | The indicator is published once a year, in the current year for the previous year. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator tracks the number of published reports on the implementation of medium-term plans of medium-term planning entities at the national level in the previous year, relative to the total number of adopted and published medium-term plans that were in force for the reporting year. The preparation and publication of reports on the implementation of medium-term plans is carried out in the current year for the previous year. A medium-term plan considered valid for the previous year is defined as a plan for which the previous reporting year represents the first year of its validity period. Formula: (Number of published reports on the implementation of medium-term plans / Total number of published medium-term plans valid for the reporting year) × 100 |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. |  | 2023. | 2024. | 2025 |
|  | 75% | 86% |  | 77% | 88% | 93% |
| Data on target value | 2026. | 2027. |  | 2028. | 2029. | 2030. |
|  | 95% | 95% |  | 95% | 95% | 95% |
| Performance assessment: | A deviation of up to 2% is allowed. |  |  |  |  |  |

Indicator at measure level 2.1

| Indicator name | Percentage of realized collection compared to the approved budget estimate (personal income tax, corporate income tax, gross domestic VAT, gross excises) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 2.1 - Efficient collection of budget revenues under the competence of the Tax Administration |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | Law on budget and Tax administration report - https://mfin.gov.rs/propisi/zakoni/1 and https://www.purs.gov.rs/o-nama/Izvestaj.html |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Tax administration |  |  |  |  |  |
| Frequency | Annually, in January of the current year for the previous year. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | This indicator measures the percentage of actual tax revenues collected against the approved budget estimate, covering personal income tax, corporate income tax, VAT (gross domestic basis), and excise duties. A level of actual collection consistent with projections indicates an efficient tax revenue collection system and contributes to the overall efficiency of the public finance system. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | 110% | 109,7% | 107,6% |  | 109,4% | 104,4% |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 100% | 100% | 100% |  | 100% | 100% |
| Performance assessment: | A deviation of up to 10% is allowed. |  |  |  |  |  |

Indicator at measure level 2.2

| Indicator name | Percentage of business entities submitting reports electronically via the portal |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 2.2 - Reduction of administrative burden and improvement of efficiency in providing electronic services under the competence of Tobacco administration |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | Portal for electronic submission of reports - https://portal.duvan.gov.rs |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Tobacco administration |  |  |  |  |  |
| Frequency | Quarterly, semi-annually, and annually in the current year for the previous year. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | This indicator measures the increase in the use of electronic services provided by the Tobacco Administration by business entities operating in the tobacco, tobacco products, and related products market. A higher level of use of electronic services is expected to improve service quality and contribute to more efficient budget revenue collection. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | 20% | 40% | 60% |  | 60% | 60% |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 70% | 100% | 100% |  | 100% | 100% |
| Performance assessment: | A deviation of up to 5% is allowed. |  |  |  |  |  |

Indicator at measure level 2.3

| Indicator name | Percentage of realized collection of customs duties in relation to the projected budget estimate |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 2.3 - Strengthening the administrative capacities of the Customs administration |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | Law on budget - https://mfin.gov.rs/propisi/zakoni/1 |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Customs administration |  |  |  |  |  |
| Frequency | Annually, in the current year for the previous year. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator tracks actual customs duty collection against the budgeted estimate for the calendar year. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  | Initial value |  |
|  | 2021. | 2022. | 2023. |  | 2024. |  |
|  | 105,49% | 99,93% | 97,89% |  | 101,64% |  |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 100% | 100% | 100% |  | 100% | 100% |
| Performance assessment: | A deviation of up to 5% is allowed. |  |  |  |  |  |

| Indicator name | Percentage of realized collection of import VAT in relation to the projected budget estimate |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 2.3 - Strengthening the administrative capacities of the Customs administration |  |  |  |  |
| Indicator type | Quantitative |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  | Higher value is better |  |  |
| Data source | Law on budget - https://mfin.gov.rs/propisi/zakoni/1 |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Customs administration |  |  |  |  |
| Frequency | Annually, in the current year for the previous year. |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator tracks actual VAT on imports collection against the budgeted estimate for the calendar year |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  | Initial value |  |
|  | 2021. | 2022. | 2023. | 2024. |  |
|  | 101,86% | 98,95% | 97,55% | 97,72% |  |
| Data on target value | 2026. | 2027. | 2028. | 2029. | 2030. |
|  | 100% | 100% | 100% | 100% | 100% |
| Performance assessment: | A deviation of up to 5% is allowed. |  |  |  |  |

Indicator at measure level 2.4

| Indicator name | Share of interest expenditures in GDP |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 2.4: Efficient public debt management |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Lower value is better |  |  |
| Data source | Ministry of Finance – Public debt administration |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Public debt administration |  |  |  |  |  |
| Frequency | Annually, in the current year for the previous year. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | Share of interest expenditures in GDP = Total interest expenditures / GDP |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | 1.6% | 1.4% | 1.7% |  | 1.8% | 2.0% |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 1.9% | 1.9% | 1.9% |  |  |  |
| Performance assessment: | If the actual value is less than or equal to the target value. |  |  |  |  |  |

Indicator at measure level 2.5

| Indicator name | Number of certified public procurement officials |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 2.5 - Strengthening the capacities of public procurement officials |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Number |  |  | Higher value is better |  |  |
| Data source | Annual report on public procurement https://jnportal.ujn.gov.rs/annual-reports-ppo-public |  |  |  |  |  |
| Name of the entity responsible for data collection | Public procurement office |  |  |  |  |  |
| Frequency | The Government submits the Annual Report of the Public Procurement Office and publishes it on the Public Procurement Portal by 31 March of the current year for the previous year. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | Total number of persons who have successfully passed the exam and obtained the certificate for public procurement officers since the introduction of the certification system. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | 4.845 | 5.026 | 5.231 |  | 5.529 | 5.790 |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 5.850 | 5.950 | 6.100 |  | 6.200 | 6.300 |
| Performance assessment: | A deviation of up to 1% from the target value is allowed. |  |  |  |  |  |

Indicator at measure level 3.1

| Indicator name | Number of developed methodological frameworks for audits |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 3.1 - Expansion of audit coverage and development of a new audit methodology under the competence of Governmental Audit Office of EU funds |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Number |  |  | Higher value is better |  |  |
| Data source | Decision of the Director of the Office on the adoption of the methodology. |  |  |  |  |  |
| Name of the entity responsible for data collection | Governmental audit office of EU funds |  |  |  |  |  |
| Frequency | Once in the cycle of PFMRP |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator represents the total number of methodological frameworks developed and adopted by the Director during the observed period. It is calculated as the total number of methodological frameworks adopted during the year, based on an official adoption decision. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | / | / | / |  | / | / |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 2 | / | / |  |  |  |
| Performance assessment: | Performance is assessed by comparing the achieved indicator value with the planned target value. The indicator is considered successfully achieved if, in 2026, two methodological frameworks are developed and adopted. No deviation is permitted. |  |  |  |  |  |

Indicator at measure level 3.2

| Indicator name | Percentage of confirmed irregularities identified during on-the-spot and administrative controls in relation to the total number of confirmed cases of irregularities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 3.2 - Strengthening the system for more efficient and effective management of EU funds and enhancing the capacity of competent institutions in the area of protection of the EU interests |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | AFIS-IMS reporting system, Annual reports on implementation of IPA programs |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Department for EU funds management |  |  |  |  |  |
| Frequency | Annually, by 15 February of the current year for the previous year. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator tracks the percentage of confirmed irregularities identified through regular on-the-spot and administrative controls carried out by the operational structure responsible for the management of EU funds, relative to the total number of confirmed irregularity cases, including those that may be reported outside the operational structure. A higher percentage of identified and confirmed irregularities within the structure is an indicator of the effective functioning of the system responsible for the management of EU funds. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | 75% | 77,8% | 68,2% |  | 85% | 85% |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 85% | 85% | 85% |  |  |  |
| Performance assessment: | A deviation of up to 5% is allowed. |  |  |  |  |  |

Indicator at measure level 3.3

| Indicator name | Percentage of inspections conducted in response to complaints included in the annual inspection plan for the current year, relative to the number of complaints received within the jurisdiction of the Budget Inspection in the previous year. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 3.3 - Increasing the efficiency and effectiveness of inspection oversight |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | Annual report on the work of the budget inspection - https://mfin.gov.rs/kontrola-javnih-sredstava/budzetska-inspekcija |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Budget inspection department |  |  |  |  |  |
| Frequency | Annually, in the current year for the previous year |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The percentage of inspections carried out in response to complaints included in the inspection plan for the current year, relative to the number of complaints received within the jurisdiction of the Budget Inspection in the previous year, is calculated as follows: The number of complaints included in the inspection plan for the current year is divided by the number of complaints received within the jurisdiction of the Budget Inspection in the previous year and expressed as a percentage. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  | Initial value |  |
|  | 2021. | 2022. | 2023. |  | 2024. |  |
|  | 26% | 40% | 37% |  | 47% |  |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 48% | 50% | 52% |  | 56% | 61% |
| Performance assessment: | Increased percentage of inspections carried out in response to complaints. No deviation is permitted. |  |  |  |  |  |

Indicator at measure level 4.1

| Indicator name | Percentage of priority public sector bodies (PSBs) submitting reports on the state of the IFC system |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 4.1 - Improvement of the internal financial control system in public sector institutions |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | Consolidated annual report - https://mfin.gov.rs/o-ministarstvu/konsolidovani-godinji-izvetaj |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Central harmonization unit |  |  |  |  |  |
| Frequency | Annually, in the current year for the previous year |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator reflects the number of public funds beneficiaries (ministries, compulsory social insurance organizations, public agencies of the Republic of Serbia, and cities) that submit reports to the Ministry of Finance on the status of the Financial Management and Control (FMC) system, thereby contributing to the overall improvement of the financial management and control system in the public sector. It is calculated as the percentage (share) of such beneficiaries out of the total number of the same categories of beneficiaries that submitted reports to the Ministry of Finance – Central Harmonisation Unit (CHU) through the reporting application. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  | Initial value |  |
|  | 2021. | 2022. | 2023. |  | 2024. |  |
|  | 93,48% | 95,83% | 96,15% |  | 86,78% |  |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 90% | 92% | 95% |  | 96% | 97% |
| Performance assessment: | A deviation of up to 1% is allowed. |  |  |  |  |  |

| Indicator name | Percentage of priority PSBs that have prepared a risk register |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 4.1 - Improvement of the internal financial control system in public sector institutions |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | Consolidated annual report - https://mfin.gov.rs/o-ministarstvu/konsolidovani-godinji-izvetaj |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Central harmonization unit |  |  |  |  |  |
| Frequency | Annually, in the current year for the previous year |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator measures the share of public funds beneficiaries (ministries, compulsory social insurance organizations, public enterprises established by the Republic of Serbia, and cities) that submit reports to the Ministry of Finance on the status of their Financial Management and Control (FMC) systems, thereby contributing to the overall improvement of financial management and control in the public sector. It is calculated as the percentage of these beneficiaries out of the total number of beneficiaries in the same categories that submitted reports to the Ministry of Finance – Central Harmonisation Unit (CHU) through the reporting application. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  | Initial value |  |
|  | 2021. | 2022. | 2023. |  | 2024. |  |
|  | 70,93% | 78,26% | 79,05% |  | 72,19% |  |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 77% | 82% | 87% |  | 88% | 90% |
| Performance assessment: | A deviation of up to 1% is allowed. |  |  |  |  |  |

Indicator at measure level 4.2

| Indicator name | Percentage of priority public sector bodies (PSBs) that have an internal auditor employed in the organization (from those required by law to have an internal audit unit) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 4.2 - Enhanced internal audit function in the public sector in accordance with international standards and principles |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | Consolidated annual report - https://mfin.gov.rs/o-ministarstvu/konsolidovani-godinji-izvetaj |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Central harmonization unit |  |  |  |  |  |
| Frequency | Annually, in the current year for the previous year |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator reflects the number of public funds beneficiaries covered by the Rulebook on Common Criteria for the Organisation and Standards and Methodological Guidelines for the Conduct and Reporting of Internal Audit in the Public Sector. It is calculated as the percentage (share) of such beneficiaries that have an internal auditor employed within the organisation, relative to the total number of beneficiaries in the same category that submitted reports to the Ministry of finance – Central harmonisation unit (CHU) through the reporting application. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  | Initial value |  |
|  | 2021. | 2022. | 2023. |  | 2024. |  |
|  | / | / | / |  | 80,82% |  |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 83% | 85% | 87% |  | 88% | 90% |
| Performance assessment: | A deviation of up to 2% is allowed. |  |  |  |  |  |

| Indicator name | Total number of improved materials in the area of internal financial control |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 4.2 - Enhanced internal audit function in the public sector in accordance with international standards and principles |  |  |  |  |  |
| Indicator type | Qualitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Number |  |  | Enhanced PIFC materials aligned with the Global Internal Audit Standards; a higher value is better. |  |  |
| Data source | Materials published on the Ministry of finance website. https://mfin.gov.rs/o-ministarstvu/materijali-za-uenje https://mfin.gov.rs/o-ministarstvu/modeli-akata-za-uspostavljanje-interne-revizije https://mfin.gov.rs/o-ministarstvu/finansijsko-upravljanje-i-kontrola https://mfin.gov.rs/o-ministarstvu/obuke |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Central harmonization unit |  |  |  |  |  |
| Frequency | Annually, in the current year for the previous year |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | Alignment of the regulatory framework and methodological materials with the Global Internal Audit Standards. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | / | / | / |  | / | 0 |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 2 | 3 | 4 |  | / | / |
| Performance assessment: | Deviation is not permitted. |  |  |  |  |  |

Indicator at measure level 4.3

| Indicator name | Total number of established modules within the IT system |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 4.3 - Improvement of IT systems to include modules for internal control and internal audit |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Number |  |  | Establishment and enhancement of modules within the IT system. |  |  |
| Data source | Consolidated annual report - https://mfin.gov.rs/o-ministarstvu/konsolidovani-godinji-izvetaj |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Central harmonization unit |  |  |  |  |  |
| Frequency | Annually, in the current year for the previous year |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | In view of the growing number of entities reporting on Financial Management and Control (FMC) and Internal Audit (IA), as well as the need to maintain internal audit registers, further enhancement of the reporting application is planned. A technical specification has been developed providing for the upgrade of the reporting module and the development of new FMC and Internal Audit modules. These modules will enable more systematic and efficient maintenance of internal audit registers, the establishment and management of a risk register, and easier monitoring of the implementation of internal audit recommendations. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | / | / | / |  | / | 1 |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 2 | 3 | / |  | / | / |
| Performance assessment: | Enhanced reporting application and developed FMC and Internal Audit (IA) modules. No deviation is permitted. |  |  |  |  |  |

Indicator at measure level 5.1

| Indicator name | Draft financial statement prepared in accordance with IPSAS on a cash basis |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 5.1: Application of IPSAS standards on a cash basis for all budget users |  |  |  |  |  |
| Indicator type | Qualitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Yes/No |  |  | Yes is better value |  |  |
| Data source | State audit institution Audit report on the Final Account of the budget of the Republic of Serbia - https://www.dri.rs/izvestaji |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Treasury administration |  |  |  |  |  |
| Frequency | Annually, in the current year for the previous year |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator reflects the strengthening of the public sector accounting system through the application of cash-basis public sector accounting standards. The preparation of a draft Financial Report in accordance with Cash-Basis IPSAS will strengthen the cash-basis accounting framework applied in the Republic of Serbia and thereby contribute to the overall strengthening of the public sector accounting system. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | / | / | / |  | / | No |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | Yes | Yes | Yes |  |  |  |
| Performance assessment: | Deviation is not permitted. |  |  |  |  |  |

Indicator at measure level 5.2

| Indicator name | Drafted Public sector accounting improvement plan in accordance with IPSAS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 5.2 - Further improvement of budget accounting according to the Public sector accounting improvement plan in line with IPSAS |  |  |  |  |  |
| Indicator type | Qualitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Yes/No |  |  | Yes is better value |  |  |
| Data source | Treasury administration website https://www.trezor.gov.rs/src/documents/regulations/ostala dokumenta/ |  |  |  |  |  |
| Name of the entity responsible for data collection | Ministry of Finance – Treasury administration |  |  |  |  |  |
| Frequency | Once in the cycle of PFMRP 2026-2030. |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator reflects the preparation of a plan for the further improvement of public sector accounting, to be implemented in phases. The adoption of the Accounting Improvement Plan aims to strengthen the overall accounting system through the application of International Public Sector Accounting Standards (IPSAS). |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | / | / | / |  | / | / |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | / | / | Yes |  |  |  |
| Performance assessment: | Deviation is not permitted. |  |  |  |  |  |

Indicator at measure level 6.1

| Indicator name | Percentage of DRI recommendations implemented within 2 years of the publication of the report |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 6.1 - Strengthening the efficiency and impact of external audit through the integration of modern technologies, improvement of methodology and communication with stakeholders |  |  |  |  |  |
| Indicator type | Qualitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | Internal reports on tracking the implementation of SAI recommendations |  |  |  |  |  |
| Name of the entity responsible for data collection | State audit institution |  |  |  |  |  |
| Frequency | Annually |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator is calculated at the end of the current year as the share of Priority 1 and Priority 2 recommendations issued to audited entities in the previous year that were implemented by those entities during the previous and current years, relative to the total number of Priority 1 and Priority 2 recommendations issued by the State Audit Institution (SAI) in the previous year. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  |  | 2024. |
|  |  |  |  |  |  | 77% |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 80% | 81% | 82% |  |  |  |
| Performance assessment: | A deviation of up to 2% is allowed. |  |  |  |  |  |

Indicator at measure level 6.2

| Indicator name | Percentage of SAI reports reviewed in the National Assembly |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 6.2 – Ensuring effective parliamentary oversight over public finances |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Percentage |  |  | Higher value is better |  |  |
| Data source | Reports and minutes of the National assembly Finance committee |  |  |  |  |  |
| Name of the entity responsible for data collection | National assembly – Committee on Finance, state budget and control of public spending |  |  |  |  |  |
| Frequency | Annually |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator relates to the collection of data on the number of State Audit Institution (SAI) reports that have been considered and adopted. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  |  |  |  |  |  | 50% |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 55% | 60% | 65% |  | 70% | 75% |
| Performance assessment: | A deviation of up to 5% is allowed. |  |  |  |  |  |

| Indicator name | Number of Committee meetings/sessions held for reviewing recommendations for amendments to laws in the presence of DRI and the Ministry of Finance, annually |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Corresponding general objective, specific objective or measure | Measure 6.2 – Ensuring effective parliamentary oversight over public finances |  |  |  |  |  |
| Indicator type | Quantitative |  |  | Output indicator |  |  |
| Unit of measure and nature | Number |  |  | Higher value is better |  |  |
| Data source | Minutes of the sessions/meetings of the National assembly Committee on finance, state budget and control of public spending. |  |  |  |  |  |
| Name of the entity responsible for data collection | National assembly – Committee on finance, state budget and control of public spending |  |  |  |  |  |
| Frequency | Annually |  |  |  |  |  |
| Brief description of the indicator and calculation methodology (Formula/Equation) | The indicator tracks the number of sessions/meetings of the Committee held to consider recommendations for legislative amendments, with the participation of the State Audit Institution (SAI) and the Ministry of Finance. |  |  |  |  |  |
| Initial value, year of measurement and historical trend data | Earlier trend |  |  |  |  | Initial value |
|  | 2021. | 2022. | 2023. |  | 2024. | 2025. |
|  | 1 | 1 | 1 |  | 1 | 1 |
| Data on target value | 2026. | 2027. | 2028. |  | 2029. | 2030. |
|  | 1 | 1 | 1 |  | 1 | 1 |
| Performance assessment: | Deviation is not permitted. |  |  |  |  |  |

TAIEX support is provided through technical assistance financed directly by the European Commission, without the allocation of a predefined budget to the beneficiary institution. In practice, this entails the provision of expert support rather than financial resources.

INTOSAI development initiative

EUROSAI – European organization of supreme audit institutions