| # Action plan for implementation of the public financial Management reform programme for the period 2026-2028. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # GENERAL OBJECTIVE: ACHIEVING SUSTAINABLE BUDGET WITH A STABLE RATIO OF PUBLIC DEBT TO GDP THROUGH BETTER FINANCIAL MANAGEMENT AND CONTROL, AUDITING AND INTEGRATION OF BUDGET PLANNING WITH GOVERNMENT POLICIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  | Action plan for Implementation of the Public Financial Management Reform Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for monitoring and control of implementation: |  |  |  |  |  |  |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Public policy document for which the action plan is determined: |  |  |  |  |  |  |  | Public Financial Management Reform Programme 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Public policy umbrella document: |  |  |  |  |  |  |  | Public Administration Reform Strategy 2021-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at general objective level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  |  |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |
| Real GDP growth |  |  |  |  |  | Percentage (%) |  |  |  | Fiscal Strategy, Economic Reform Programme |  |  |  |  |  |  |  | 3,9 |  |  |  |  |  | 2024 |  |  |  | 4,2 |  |  |  |  |  |  | 5,0 |  |  |  |  | 3,5 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| General government debt level in GDP |  |  |  |  |  | Percentage (%) |  |  |  | Fiscal Strategy, Economic Reform Programme |  |  |  |  |  |  |  | 46,9 |  |  |  |  |  | 2024 |  |  |  | 44,5 |  |  |  |  |  |  | 44,3 |  |  |  |  | 44,1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # SPECIFIC OBJECTIVE I: CAPACITY FOR BUDGET PLANNING AND PUBLIC INVESTMENT MANAGEMENT IMPROVED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at specific objective level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  |  |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |
| General Government deficit up to 3% of GDP |  |  |  |  |  | Percentage (%) |  |  |  | Revised Fiscal Strategy |  |  |  |  |  |  |  | 2 |  |  |  |  |  | 2024 |  |  |  | 3 |  |  |  |  |  |  | 3 |  |  |  |  | 2,5 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Measure 1.1: Improvement of the Programme Budget and Medium-term Expenditure Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Institution responsible for implementation (coordination of implementation): Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Implementation period: 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ## Measure type: Informative and educational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  |  |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |
| Percentage of healthcare institutions applying the programme budget |  |  |  |  |  | Percentage (%) |  |  |  | Software for budget preparation of healthcare institutions |  |  |  |  |  |  |  | 0 |  |  |  |  |  | 2025 |  |  |  | 0 |  |  |  |  |  |  | 70 |  |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity name: |  |  |  |  |  | Deadline for completion of the activity |  | Institution responsible for implementation |  | Partners in the implementation of activity |  |  |  |  |  |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  | Link to programme budget (PR-PA/PJ) |  |  |  | 2026 |  |  |  |  |  |  | 2027 |  |  |  |  | 2028 |  |  |  |  | 2029 |  |  |  |  |  |  | 2030 |  |
| 1.1.1 Introduction of programme budgeting in healthcare institutions |  |  |  |  |  | Q4 2026 |  | Ministry of Finance |  | Republic fund of health insurance |  |  |  |  |  |  |  | IPA2021 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 Development of methodologies and manuals for all levels of government |  |  |  |  |  | Q4 2027 |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.3 Improvement of modules for monitoring and evaluation of programme performance and preparation of a consolidated performance report |  |  |  |  |  | Q4 2028 |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.4 Improvement of the system and development models for more credible expenditure projections and increased budget transparency |  |  |  |  |  | Q4 2028 |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Measure 1.2: Strengthening institutional capacities and improving the methodological framework for green budgeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Institution responsible for implementation (coordination of implementation): Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Implementation period: 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ## Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  |  |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |
| Coverage of the application of the green budgeting methodology across all levels of government |  |  |  |  |  | Percentage (%) |  |  |  | Ministry of Finance report |  |  |  |  |  |  |  | 50 |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity name: |  |  |  |  |  | Deadline for completion of the activity |  | Institution responsible for implementation |  | Partners in the implementation of activity |  |  |  |  |  |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  | Link to programme budget (PR-PA/PJ) |  |  |  | 2026 |  |  |  |  |  |  | 2027 |  |  |  |  | 2028 |  |  |  |  | 2029 |  |  |  |  |  |  | 2030 |  |
| 1.2.1 Organization of workshops for budget analysts to strengthen capacities for green budgeting |  |  |  |  |  | 4Q 2028 |  | Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |
| 1.2.2 Expansion of the scope of the green budgeting methodology in terms of types of expenditures and levels of government |  |  |  |  |  | 4Q 2028 |  | Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 Strengthening the capacities of the green budgeting working group through training and workshops |  |  |  |  |  | 4Q 2028 |  | Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.4. Study visit – example of good practice in green budgeting |  |  |  |  |  | 4Q 2028 |  | Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # Measure 1.3: Harmonization of the budget process in the Republic of Serbia with the budget process in the European Union |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Institution responsible for implementation (coordination of implementation): Public Policy Secretariat |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # Implementation period: 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | # Measure type: Informative and educational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  |  |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |
| Percentage of trained budget analysts in the Ministry of Finance |  |  |  |  |  | Percentage (%) |  |  |  | Ministry of Finance report |  |  |  |  |  |  |  | 0 |  |  |  |  |  | 2025 |  |  |  | 30 |  |  |  |  |  |  | 70 |  |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity name: |  |  |  |  |  | Deadline for completion of the activity |  | Institution responsible for implementation |  | Partners in the implementation of activity |  |  |  |  |  |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  | Link to programme budget (PR-PA/PJ) |  |  |  | 2026 |  |  |  |  |  |  | 2027 |  |  |  |  | 2028 |  |  |  |  | 2029 |  |  |  |  |  |  | 2030 |  |
| 1.3.1 Analyses of the budget preparation process in the Republic of Serbia and its alignment with the budget process in EU countries |  |  |  |  |  | Q4 2027 |  | Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 Development of guidelines for harmonizing the budget process with EU standards |  |  |  |  |  | Q4 2028 |  | Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.3 Strengthening the capacities of budget analysts for budget preparation in accordance with EU regulations |  |  |  |  |  | Q4 2028 |  | Ministry of Finance – Budget department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Measure 1.4: Improvement of the environment for efficient management of capital projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Institution responsible for implementation (coordination of implementation): Ministry of Finance – Department for Capital Projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Regulatory |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  |  |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |
| Percentage of capital projects included in the budget, subject to assessment and evaluated in accordance with the methodology governing capital projects |  |  |  |  |  | Percentage (%) |  |  |  | Budget law/Commission for Capital Investments |  |  |  |  |  |  |  | 60 |  |  |  |  |  | 2025 |  |  |  | 70 |  |  |  |  |  |  | 75 |  |  |  |  | 80 |  |  |  |  | - |  |  |  |  |  |  | - |  |
| Activity name: |  |  |  |  |  | Deadline for completion of the activity |  | Institution responsible for implementation |  | Partners in the implementation of activity |  |  |  |  |  |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  | Link to programme budget (PR-PA/PJ) |  |  |  | 2026 |  |  |  |  |  |  | 2027 |  |  |  |  | 2028 |  |  |  |  | 2029 |  |  |  |  |  |  | 2030 |  |
| 1.4.1 Amendments and supplements to the legal framework in accordance with identified weaknesses in practical implementation |  |  |  |  |  | Q4 2026 |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  | - |  |  |  |  |  |  | - |  |
| 1.4.2 Improvement and standardization of public reports on the status of capital projects monitored in accordance with the methodology |  |  |  |  |  | Q4 2027 |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  | - |  |  |  |  |  |  | - |  |
| 1.4.3 Familiarization of the officials from Department for Capital Projects with good international practices related to planning, monitoring and reporting in the field of public investments (through study visits, workshops, etc.) |  |  |  |  |  | Q4 2026 |  | Ministry of Finance |  | World Bank, SECO, IMF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |
| 1.4.4 Preparation of a manual on the methodology in the field of capital projects (design, preparation for printing, proofreading, consulting support for content) |  |  |  |  |  | Q1 2028 |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  | - |  |
| ## Measure 1.5: Strengthening the capacities of the Section for fiscal risk monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Section for fiscal risk monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Implementation period: 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ## Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  |  |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |
| Published report on fiscal risks |  |  |  |  |  | Published/Not published |  |  |  | Ministry of Finance website |  |  |  |  |  |  |  | / |  |  |  |  |  | 2026 |  |  |  | Published |  |  |  |  |  |  | / |  |  |  |  | / |  |  |  |  | / |  |  |  |  |  |  | / |  |
| Revised methodology for monitoring fiscal risks related to the operations of state-owned enterprises and local governments |  |  |  |  |  | Adopted/Not adopted |  |  |  | Official gazette of the Republic of Serbia |  |  |  |  |  |  |  | / |  |  |  |  |  | 2027 |  |  |  | / |  |  |  |  |  |  | Adopted |  |  |  |  | / |  |  |  |  | / |  |  |  |  |  |  | / |  |
| Activity name: |  |  |  |  |  | Deadline for completion of the activity |  | Institution responsible for implementation |  | Partners in the implementation of activity |  |  |  |  |  |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  | Link to programme budget (PR-PA/PJ) |  |  |  | 2026 |  |  |  |  |  |  | 2027 |  |  |  |  | 2028 |  |  |  |  | 2029 |  |  |  |  |  |  | 2030 |  |
| 1.5.1 Improvement and standardization of reporting on fiscal risks |  |  |  |  |  | Q4 2026 |  | Ministry of Finance, Department for fiscal risks monitoring |  | World bank |  |  |  |  |  |  |  | Budget of Republic of Serbia, Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.2 Revision of the methodology for monitoring fiscal risks related to the operations of state-owned enterprises and local governments |  |  |  |  |  | Q4 2027 |  | Ministry of Finance, Department for fiscal risks monitoring |  | World bank |  |  |  |  |  |  |  | Budget of Republic of Serbia, Donor funds |  |  |  |  |  | 2301 (Regular allocations) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.3 Development of methodology for linking budget reserves with quantified risk indicators |  |  |  |  |  | Q4 2028 |  | Ministry of Finance, Department for fiscal risks monitoring |  | World bank |  |  |  |  |  |  |  | Budget of Republic of Serbia, Donor funds |  |  |  |  |  | 2031 (Regular allocations) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.4 Development of a methodology for monitoring fiscal risks from climate change |  |  |  |  |  | Q4 2028 |  | Ministry of Finance, Department for fiscal risks monitoring |  | World bank |  |  |  |  |  |  |  | Budget of Republic of Serbia, Donor funds |  |  |  |  |  | 2031 (Regular allocations) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 1.6: Establishment of a system for coordination and management of EU own resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance - Macroeconomic and fiscal projections and analyses department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Informative and educational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  |  |  |  | Unit of measure |  | Source of verification |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |  |  |  |  | Target value 2029 |  |  | Target value 2030 |  |  |  |  |  |
| Level of progress within Negotiation chapter 33 |  |  |  |  | 1.No progress achieved 2.Limited progress 3.Some progress |  | European Commission’s annual report on Serbia |  |  | 1.No progress achieved |  |  |  |  |  | 2024 |  |  |  | 2.Limited progress |  |  |  |  | 3.Some progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity name: |  |  |  |  | Deadline for completion of the activity |  | Institution responsible for implementation |  |  | Partners in the implementation of activity |  |  |  |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  | Link to programme budget (PR-PA/PJ) |  |  |  |  | 2026 |  |  |  | 2027 |  |  |  |  |  | 2028 |  |  |  |  |  |  |  |  |  | 2029 |  |  | 2030 |  |  |  |  |  |
| 1.6.1 Establishment of operational and procedural links between institutions with the aim of improving coordination and data exchange in accordance with the obligations of Chapter 33 |  |  |  |  | Q4 2026 |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.2 Development and improvement of systems, processes and procedures in organizational and informational, i.e. technical and technological terms |  |  |  |  | Q4 2028 |  | Ministry of Finance |  |  | NBS, Republic secretariat for legislation, Ministry for Environment protection |  |  |  |  |  | Budget of RS and IPA2022 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.3 Establishment and development of administrative capacities |  |  |  |  | Q4 2028 |  | Ministry of Finance |  |  | NBS, Republic secretariat for legislation, Ministry for Environment protection |  |  |  |  |  | Budget of RS and IPA2022 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 1.7: Improvement of medium-term planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: Public policy secretariat (PPS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Informative and educational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  |  |  |  | Unit of measure |  | Source of verification |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  |  |  |  |  |  | Target value 2029 |  |  | Target value 2030 |  |  |  |  |  |
| Number of adopted and published medium-term plans of entities obliged to conduct medium-term planning at the republic level |  |  |  |  | Number |  | Websites of entities obliged to conduct medium-term planning |  |  | 29 |  |  |  |  |  | 2025 |  |  |  | 30 |  |  |  |  | 32 |  |  |  |  |  |  |  |  |  | 34 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Percentage of published reports on the implementation of medium-term plans in relation to the total number of published medium-term plans valid for the year being reported on |  |  |  |  | Percentage % |  | Websites of entities obliged to conduct medium-term planning |  |  | 92 |  |  |  |  |  | 2024 |  |  |  | 95 |  |  |  |  | 95 |  |  |  |  |  |  |  |  |  | 95 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity name: |  |  |  |  | Deadline for completion of the activity |  | Institution responsible for implementation |  |  | Partners in the implementation of activity |  |  |  |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  | Link to programme budget (PR-PA/PJ) |  |  |  |  | 2026 |  |  |  | 2027 |  |  |  |  |  | 2028 |  |  |  |  |  |  |  |  |  | 2029 |  |  | 2030 |  |  |  |  |  |
| 1.7.1 Mentorship support in the preparation of medium-term plans of entities obliged to conduct medium-term planning at the republic level, for better alignment with annual budgets of the entities |  |  |  |  | Q4 2028 |  | PPS |  |  | Entities obliged to conduct medium-term planning |  |  |  |  |  | 01-Budget of RS/regular allocations |  |  |  | 0610-0006 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # SPECIFIC OBJECTIVE II: EFFICIENT COLLECTION AND MANAGEMENT OF BUDGET FUNDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at specific objective level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  |  |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |
| Actual revenues and expenditures of the state sector budget on an annual basis are within 5% of those projected in the fiscal strategy |  |  |  |  |  | Percentage (%) |  |  |  | Fiscal strategy |  |  |  |  |  |  |  | Within the range of up to 5 |  |  |  |  |  | 2025 |  |  |  | Within the range of up to 5 |  |  |  |  |  |  | Within the range of up to 5 |  |  |  |  | Within the range of up to 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Measure 2.1: Efficient collection of budget revenues under the competence of the Tax Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Tax Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Implementation period: 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ## Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  |  |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |
| Percentage of realized collection compared to the approved budget estimate (personal income tax, corporate income tax, gross domestic VAT, gross excises) |  |  |  |  |  | Percentage (%) |  |  |  | Law on budget and Tax administration report |  |  |  |  |  |  |  | 109,8 |  |  |  |  |  | 2024 |  |  |  | 100 |  |  |  |  |  |  | 100 |  |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity name: |  |  |  |  |  | Deadline for completion of the activity |  | Institution responsible for implementation |  | Partners in the implementation of activity |  |  |  |  |  |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  | Link to programme budget (PR-PA/PJ) |  |  |  | 2026 |  |  |  |  |  |  | 2027 |  |  |  |  | 2028 |  |  |  |  | 2029 |  |  |  |  |  |  | 2030 |  |
| 2.1.1 Implementation of a ready-made commercial solution for an Integrated Tax Management Information System (COTS-ITMS) |  |  |  |  |  | Q4 2028 |  | Ministry of Finance, Tax administration |  |  |  |  |  |  |  |  |  | The signing of the Law on the ratification of Loan agreement (additional financing for TAMP) between the Republic of Serbia and International bank for reconstruction and development is pending. |  |  |  |  |  | TAMP project (loan 8936-YF) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 Improved training function within the Tax Administration of the Republic of Serbia |  |  |  |  |  | Q2 2027 |  | Ministry of Finance, Tax administration |  |  |  |  |  |  |  |  |  | IPA 2022 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 Further harmonization of national legislation and development of a roadmap relevant for supporting the implementation of international information exchange systems |  |  |  |  |  | Q4 2027 |  | Ministry of Finance, Tax administration |  |  |  |  |  |  |  |  |  | VIES - IPA 2021 (for other systems, the source of financing will be provided subsequently) |  |  |  |  |  | UNDP (loan 8936-YF) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4 Enhanced strategic competencies for human resource management |  |  |  |  |  | Q4 2027 |  | Ministry of Finance, Tax administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.5 Introduction of a preliminary VAT return through the upgrade of the e-Invoice system |  |  |  |  |  | Q1 2027 |  | Ministry of Finance, Department for digitalization in the field of finance |  | Tax administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.6 Improvement of the e-Delivery Note system |  |  |  |  |  | Q4 2027 |  | Ministry of Finance, Department for digitalization in the field of finance |  | Inspection authorities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.7 Establishment of a module for tracking tobacco products through the improvement of the e-Excise system |  |  |  |  |  | Q1 2027 |  | Ministry of Finance, Department for digitalization in the field of finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Measure 2.2: Reduction of administrative burden and improvement of efficiency in providing electronic services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Tobacco administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Implementation period: 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ## Measure type: Informative and educational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  |  |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |
| Percentage of business entities submitting reports electronically via the portal |  |  |  |  |  | Percentage (%) |  |  |  | Portal for electronic submission of reports |  |  |  |  |  |  |  | 0 |  |  |  |  |  | 2025 |  |  |  | 70 |  |  |  |  |  |  | 100 |  |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  |  | - |  |
| Activity name: |  |  |  |  |  | Deadline for completion of the activity |  |  |  | Institution responsible for implementation |  |  |  |  |  |  |  | Partners in the implementation of activity |  |  |  |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  | Link to programme budget (PR-PA/PJ) |  |  |  |  |  |  | 2026 |  |  |  |  | 2027 |  |  | 2028 |  |  |  |  |  |  | 2029 |  |  | 2030 |
| 2.2.1 Preparation, publication, and implementation of video trainings and guidelines to support business entities in using the portal |  |  |  |  |  | Q4 2026 |  |  |  | Tobacco administration |  |  |  |  |  |  |  |  |  |  |  |  |  | *Budget/Donor funds |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  | - |  |  | - |  |  |  |  |  |  | - |  |  | - |
| 2.2.2 Improvement of the efficiency of processing reports submitted through the portal |  |  |  |  |  | Q4 2027 |  |  |  | Tobacco administration |  |  |  |  |  |  |  |  |  |  |  |  |  | Budget funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  | - |  |  |  |  |  |  | - |  |  | - |
| ## Measure 2.3: Strengthening the administrative capacities of the Customs administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance – Customs administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Implementation period: 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ## Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  |  |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |
| Percentage of realized collection of customs duties compared to the approved budget estimate |  |  |  |  |  | Percentage (%) |  |  |  | Law on budget |  |  |  |  |  |  |  | Customs 101,64 |  |  |  |  |  | 2024 |  |  |  | 100 |  |  |  |  |  |  | 100 |  |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Percentage of realized collection of import VAT compared to the approved budget estimate |  |  |  |  |  | Percentage (%) |  |  |  | Law on budget |  |  |  |  |  |  |  | VAT 97,72 |  |  |  |  |  | 2024 |  |  |  | 100 |  |  |  |  |  |  | 100 |  |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity name: |  |  |  |  |  | Deadline for completion of the activity |  | Institution responsible for implementation |  | Partners in the implementation of activity |  |  |  |  |  |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  | Link to programme budget (PR-PA/PJ) |  |  |  | 2026 |  |  |  |  |  |  | 2027 |  |  |  |  | 2028 |  |  |  |  | 2029 |  |  |  |  |  |  | 2030 |  |
| 2.3.1 Upgrade of the NCTS transit procedure application |  |  |  |  |  | Q4 2028 |  | Customs administration |  | - |  |  |  |  |  |  |  | Budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 Improvement of capacities for effective post-clearance audits, determination of customs value, preferential origin, and classification of goods |  |  |  |  |  | Q4 2027 |  | Customs administration |  |  |  |  |  |  |  |  |  | IPA unallocated |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  | - |  |
| 2.3.3 Modernization of the customs laboratory |  |  |  |  |  | Q4 2027 |  | Customs administration |  |  |  |  |  |  |  |  |  | IPA2026 |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  | - |  |  |  |  | - |  |  |  |  |  |  | - |  |
| 2.3.4 Implementation of import and export automated systems (AIS-AES) and control system (CDS) |  |  |  |  |  | Q4 2027 |  | Customs administration |  |  |  |  |  |  |  |  |  | IPA2020 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |
| 2.3.5 Development of a system for collection of budget revenues, collection monitoring, and integration with automated systems |  |  |  |  |  | Q4 2027 |  | Customs administration |  |  |  |  |  |  |  |  |  | Budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |
| 2.3.6 Procurement of software and hardware for integrated tariff management (ITMS) |  |  |  |  |  | Q4 2026 |  | Customs administration |  |  |  |  |  |  |  |  |  | IPA2021 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.7 Procurement of a data warehouse for storing customs data |  |  |  |  |  | Q4 2027 |  | Customs administration |  |  |  |  |  |  |  |  |  | IPAIII |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Measure 2.4: Efficient public debt management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance - Public debt administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Implementation period: 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ## Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  |  |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |
| Share of debt in domestic currency |  |  |  |  |  | Percentage (%) |  |  |  | Annual report on work of Public debt administration |  |  |  |  |  |  |  | 21,8 |  |  |  |  |  | 2024 |  |  |  | 23 |  |  |  |  |  |  | 24 |  |  |  |  | 25 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity name: |  |  |  |  |  | Deadline for completion of the activity |  | Institution responsible for implementation |  | Partners in the implementation of activity |  |  |  |  |  |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  | Link to programme budget (PR-PA/PJ) |  |  |  | 2026 |  |  |  |  |  |  | 2027 |  |  |  |  | 2028 |  |  |  |  | 2029 |  |  |  |  |  |  | 2030 |  |
| 2.4.1 Expansion of reporting scope (units) through development and implementation of an Information System for submission of financial reports |  |  |  |  |  | Q4 2027 |  | Public debt administration |  | - |  |  |  |  |  |  |  | Budget |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  | - |  |  |  |  |  |  | - |  |
| 2.4.2 Issuance of green/sustainable Eurobonds on the international market |  |  |  |  |  | Q4 2028 |  | Public debt administration |  | - |  |  |  |  |  |  |  | Budget |  |  |  |  |  | - |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |
| 2.4.3 Issuance of green/sustainable government bonds on the domestic market |  |  |  |  |  | Q4 2028 |  | Public debt administration |  | - |  |  |  |  |  |  |  | Budget |  |  |  |  |  | - |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  | - |  |  |  |  | - |  |  |  |  |  |  |  |  |
| 2.4.4 Improvement of reporting through the application of business intelligence tools within the existing information system (PDMS) |  |  |  |  |  | Q4 2028 |  | Public debt administration |  | - |  |  |  |  |  |  |  | Donor funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Measure 2.5: Strengthening the capacities of public procurement officials |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Institution responsible for implementation (coordination of implementation) of the measure: Public procurement office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Implementation period: 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ## Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  |  |  |  | Initial value |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |
| Number of certified public procurement officials |  |  |  |  |  | Number |  |  |  | Annual report on public procurement |  |  |  |  |  |  |  | 5529 |  |  |  |  |  | 2024 |  |  |  | 5650 |  |  |  |  |  |  | 5800 |  |  |  |  | 5950 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity name: |  |  |  |  |  | Deadline for completion of the activity |  | Institution responsible for implementation |  | Partners in the implementation of activity |  |  |  |  |  |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  | Link to programme budget (PR-PA/PJ) |  |  |  | 2026 |  |  |  |  |  |  | 2027 |  |  |  |  | 2028 |  |  |  |  | 2029 |  |  |  |  |  |  | 2030 |  |
| 2.5.1 Trainings for exam preparation for public procurement officers |  |  |  |  |  | Q4 2028 continued |  | Public procurement office |  | NALED, Chamber of commerce and industry of Serbia, EU/UNDP |  |  |  |  |  |  |  | Budget revenues/regular allocations for salaries, appropriations 411 and 412 *Donor funds |  |  |  |  |  | 0612 – 0001 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.2 Development of practical tools for public procurement officers for applying the Public Procurement Law and using the Public Procurement Portal |  |  |  |  |  | Q4 2028 continued |  | Public procurement office |  | NALED, Chamber of commerce and industry of Serbia, EU/UNDP |  |  |  |  |  |  |  | Budget revenues/regular allocations for salaries, appropriations 411 and 412 *Donor funds |  |  |  |  |  | 0612 – 0001 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.3 Trainings and workshops for public procurement officers on planning and market research |  |  |  |  |  | Q4 2028 continued |  | Public procurement office |  | NALED, Chamber of commerce and industry of Serbia, EU/UNDP |  |  |  |  |  |  |  | Budget revenues/regular allocations for salaries, appropriations 411 and 412 *Donor funds |  |  |  |  |  | 0612-0001 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.4 Trainings and workshops for public procurement officers on conflict of interest and corruption prevention and the use of ESPD criteria |  |  |  |  |  | Q4 2028 continued |  | Public procurement office |  | NALED, Chamber of commerce and industry of Serbia, EU/UNDP |  |  |  |  |  |  |  | Budget revenues/regular allocations for salaries, appropriations 411 and 412 *Donor funds and 412 |  |  |  |  |  | 0612-0001 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # SPECIFIC OBJECTIVE III: IMPROVING BUDGET DISCIPLINE AND MORE TRANSPARENT USE OF PUBLIC FUNDS. Indicator(s) at specific objective level (outcome indicator); Unit of measure; Source of verification; Initial value; Base year; Target value 2026; Target value 2027; Target value 2028; Target value 2029; Target value 2030. Level of achieved progress within Negotiating Chapter 22; - No progress achieved - Limited progress - Some progress; Annual report; Some progress; 2024; Limited progress; Limited progress; Some progress. ## Measure 3.1: Expansion of audit coverage and development of a new audit methodology. Institution responsible for implementation (coordination of implementation) of the measure: Governmental Audit Office of EU funds. Implementation period: 2026-2030; Measure type:. Indicator(s) at measure level (outcome indicator); Unit of measure; Source of verification; Initial value; Base year; Target value 2026; Target value 2027; Target value 2028; Target value 2029; Target value 2030. Number of developed methodological frameworks for audits; Number; Decision on adoption; 0; 2025; 2. Activity name:; Deadline for completion of the activity; Institution responsible for implementation; Partners in the implementation of activity; Financial resources. Source of funds; Link to programme budget (PR-PA/PJ); 2026; 2027; 2028; 2029; 2030. 3.1.1 Staffing the internal audit group of the General Secretariat and Government services by hiring internal auditors; Q4 2026; Governmental Audit Office of EU funds; Human resources management service; Budget of RS. ## 3.1.2 Development of an audit methodological framework for IPARD III (measures 4 and 5) in accordance with EU requirements; ## Q4 2026; ## Governmental Audit Office of EU funds; ## TAIEX. ## 3.1.3 Development of a methodological framework for auditing the Reform and Growth Instrument; ## Q4 2026; ## Governmental Audit Office of EU funds; ## Donor funds. ## 3.1.4 Development of capacities for control and audit of the Reform and Growth Instrument through targeted trainings; ## Q4 2026; ## Governmental Audit Office of EU funds, Ministry of Finance, Ministry for European Integration, SAI; ## Donor funds. ## Measure 3.2: Strengthening the system for more efficient and effective management of EU funds and enhancing the capacity of competent institutions in the area of protection of the EU’s financial interests. ## Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance - Department for EU funds management. ## Implementation period: 2026-2030; ## Measure type: Institutional management organizational. Indicator(s) at measure level (outcome indicator); Unit of measure; Source of verification; Initial value; Base year; Target value 2026; Target value 2027; Target value 2028; Target value 2029; Target value 2030. Percentage of confirmed irregularities identified during on-the-spot and administrative controls in relation to the total number of confirmed cases of irregularities; Percentage (%); AFIS-IMS reporting system Annual reports on implementation of IPA programs; 85; 2025; 85; 85; 85. Activity name:; Deadline for completion of the activity; Institution responsible for implementation; Partners in the implementation of activity; Financial resources. Source of funds; Link to programme budget (PR-PA/PJ); 2026; 2027; 2028; 2029; 2030. 3.2.1 Coordination of the preparation of a plan for the implementation of continuous professional trainings related to management and supervision within the system for indirect management of EU funds.; Q4 2028; Ministry of Finance, Department for EU funds management; NAPA; Budget of RS; 4004-3212. 3.2.2 Ensuring an adequate number of civil servants and enhancing the capacity of all participants in the process of managing European Union funds.; Q4 2028; Ministry of Finance, Department for EU funds management; Human resources management service; Budget of RS; 4004-3212. 3.2.3 Supplementing and amending relevant national regulations regarding the use of Guidelines for the application of financial corrections and adoption of Guidelines for the application of financial corrections related to the use of EU funds.; Q4 2026; Ministry of Finance, Department for EU funds management; Budget of RS; 4004-3212. 3.2.4 Preparation and adoption of the Strategic Plan 2028–2030 to improve the work of national institutions relevant to the protection of the EU’s financial interests.; Q4 2027; Ministry of Finance - AFCOS; AFCOS network; Donor funds. 3.2.5 Organization of a regional conference/seminar to exchange experiences in combating fraud.; Q4 2027; Ministry of Finance - AFCOS; European anti-fraud office (OLAF); Donor funds. ## Measure 3.3: Increasing the efficiency and effectiveness of inspection oversight. ## Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance - Budget inspection department. Implementation period: 2026-2030; Measure type: Institutional management organizational. Indicator(s) at measure level (outcome indicator); Unit of measure; Source of verification; Initial value; Base year; Target value 2026; Target value 2027; Target value 2028; Target value 2029; Target value 2030. Percentage of inspections carried out based on complaints included in the inspection plan for the current year in relation to the number of complaints received under the competence of the budget inspection in the previous year..; Percentage (%); Annual report on the work of the budget inspection; 47; 2024; 48; 50; 52. Activity name:; Deadline for completion of the activity; Institution responsible for implementation; Partners in the implementation of activity; Financial resources. Source of funds; Link to programme budget (PR-PA/PJ); 2026; 2027; 2028; 2029; 2030. 3.3.1 Adoption of a Guide for planning and oversight of the budget inspection (standards of work of the budget inspection); Q1 2026; Ministry of Finance, Budget inspection department; -; Donor funds (GIZ) - (Public Finance Reform Project – Financing Agenda 2030); -; -; -. 3.3.2 Professional development of budget inspectors and other employees in the budget inspection through continuous education; Q4 2028; Ministry of Finance, Budget inspection department; -. 3.3.3 Ensuring the required number of employees – 66; Q4 2028; Ministry of Finance, Budget inspection department; -; 66. # SPECIFIC OBJECTIVE IV: IMPROVEMENT OF THE APPLICATION OF THE INTERNAL FINANCIAL CONTROL SYSTEM IN THE PUBLIC SECTOR. Indicator(s) at specific objective level (outcome indicator); Unit of measure; Source of verification; Initial value; Base year; Target value 2026; Target value 2027; Target value 2028; Target value 2029; Target value 2030. Level of progress identified in the area of Internal Financial Control in the EC progress report on the Republic of Serbia for the given year; 1.Early stage of preparedness 2.Certain level of preparedness 3.Moderate preparedness 4.Good level of preparedness; EC report on Serbia for the given year (Chapter 32); Moderate preparedness; 2025; Moderate preparedness; Good level of preparedness; Good level of preparedness. Measure 4.1: Improvement of the internal financial control system in public sector institutions. Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance - Central harmonization unit. Implementation period: 2026-2030; Measure type: Institutional management organizational. Indicator(s) at measure level (outcome indicator); Unit of measure; Source of verification; Initial value; Base year; Target value 2026; Target value 2027; Target value 2028; Target value 2029; Target value 2030. Percentage of priority public sector bodies (PSBs) submitting reports on the state of the IFC system; Percentage (%); Consolidated annual report; 86,78; 2024; 90; 92; 95. Percentage of priority PSBs that have prepared a risk register; Percentage (%); Consolidated annual report; 72,19%; 2024; 77; 82; 87. Activity name:; Deadline for completion of the activity; Institution responsible for implementation; Partners in the implementation of activity; Financial resources. Source of funds; Link to programme budget (PR-PA/PJ); 2026; 2027; 2028; 2029; 2030. 4.1.1 Improvement of risk management implementation through support to PSBs; Q4 2027; CHU; Donor funds; -; -. 4.1.2 Enhancement of the annual IFC reporting questionnaire for the priority group of PSBs; Q4 2027; CHU; -; Donor funds; -; -. 4.1.3 Development of an internal act model – a model for managing irregularities; Q4 2027; CHU; Ministry of Public administration and local self-government and Agency for prevention of corruption; Donor funds; -; -. 4.1.4 Promotion of IFC – application of good practices in priority public sector bodies; Q4 2027; CHU; Public administration bodies; Donor funds; -; -. ## Measure 4.2: Enhanced internal audit function in the public sector in accordance with international standards and principles. ## Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance - Central harmonization unit. ## Implementation period: 2026-2030; Measure type:. Indicator(s) at measure level (outcome indicator); Unit of measure; Source of verification; Initial value; Base year; Target value 2026; Target value 2027; Target value 2028; Target value 2029; Target value 2030. Percentage of priority public sector bodies (PSBs) that have an internal auditor employed in the organization (from those required by law to have an internal audit unit); Percentage (%); Consolidated annual report; 75,34; 2024; 80; 84; 87. Total number of improved materials in the area of internal financial control in the public sector (IFC); Number; Materials published on website; 0; 2025; 2; 3; 4. Activity name:; Deadline for completion of the activity; Institution responsible for implementation; Partners in the implementation of activity; Financial resources. Source of funds; Link to programme budget (PR-PA/PJ); 2026; 2027; 2028; 2029; 2030. 4.2.1 Improvement of the regulatory framework and methodological materials (rulebooks and manuals) in accordance with new international standards; Q4 2026; CHU; Donor funds; -; -. 4.2.2 Enhancement of the certification process for obtaining the title of Chief Internal Auditor (CIA) in public sector bodies; Q4 2026; CHU; Donor funds; -; -. 4.2.3 Thematic workshops in the field of internal audit; Q4 2028; CHU; Donor funds; -. 4.2.4 Development of a model Charter, Strategic and Annual Plan based on the risk matrix for the audit universe, and conducting horizontal audits; Q4 2026; Governmental Audit Office of EU funds; CHU; Budget of RS. Measure 4.3: Improvement of IT systems to include modules for internal control and internal audit. ## Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance - Central harmonization unit. Implementation period: 2026-2030; Measure type: Institutional management organizational. Indicator(s) at measure level (outcome indicator); Unit of measure; Source of verification; Initial value; Base year; Target value 2026; Target value 2027; Target value 2028; Target value 2029; Target value 2030. Total number of established modules within the IT system; Number; 1; 2025; 2; 3. Activity name:; Deadline for completion of the activity; Institution responsible for implementation; Partners in the implementation of activity; Financial resources. Source of funds; Link to programme budget (PR-PA/PJ); 2026; 2027; 2028; 2029; 2030. 4.3.1 Improvement of the reporting application and development of software for internal audit; Q4 2028; CHU; Budget funds Donor funds. |
| # SPECIFIC OBJECTIVE V: IMPROVED ACCOUNTING IN THE PUBLIC SECTOR THROUGH THE APPLICATION OF INTERNATIONAL PUBLIC SECTOR ACCOUNTING STANDARDS (IPSAS) AND THE INTRODUCTION OF ACCOUNTING STANDARDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at specific objective level (outcome indicator) |  |  |  |  |  | Unit of measure |  | Source of verification |  |  |  |  | Initial value |  |  |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |  |  |
| Improved quality of financial statements in terms of the application of cash-based IPSAS, according to the SAI (State Audit Institution) report on the audit of the budget final account |  |  |  |  |  | Yes No |  | Annual report of SAI or SAI report on the audit of the budget final account of the Republic of Serbia |  |  |  |  | No |  |  |  |  |  |  | 2025 |  |  | Yes |  |  |  |  |  |  | Yes |  |  |  |  |  | Yes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Меasure 5.1:: Application of IPSAS standards on a cash basis for all budget users |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance - Treasury administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  | Unit of measure |  |  |  | Source of verification |  |  | Initial value |  |  | Base year |  |  |  |  |  |  | Target value 2026 |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  | Target value 2028 |  |  |  |  |  |  |  | Target value 2029 |  |  |  |  | Target value 2030 |  |  |  |  |  |  |  |  |
| Draft financial statement prepared in accordance with IPSAS on a cash basis |  | Yes No |  |  |  | SAI report |  |  | No |  |  | 2025 |  |  |  |  |  |  | Yes |  |  |  |  |  |  |  | Yes |  |  |  |  |  | Yes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity name: |  |  | Deadline for completion of the activity |  |  | Institution responsible for implementation |  |  | Partners in the implementation of activity |  |  |  |  |  |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  | Link to programme budget (PR-PA/PJ) |  |  |  |  | 2026 |  |  |  |  |  | 2027 |  |  |  |  | 2028 |  |  |  |  |  |  | 2029 |  |  |  |  |  |  | 2030 |  |  |  |
| 5.1.1 Preparation and submission of financial statements in accordance with IPSAS on a cash basis |  |  | Q2 2026 |  |  | Treasury administration |  |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1.2 Preparation of notes and additional explanations accompanying the financial statements in accordance with IPSAS on a cash basis |  |  | Q2 2026 |  |  | Treasury administration |  |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1.3 Conducting trainings to improve the professional competence of public sector accountants in accordance with the Professional Training Program for bookkeeping, preparation, and presentation of financial statements in accordance with IPSAS on a cash basis |  |  | Q4 2028 |  |  | Treasury administration |  |  | NAPA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 5.2: Further improvements of budget accounting according to the Public sector accounting improvement plan in line with IPSAS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Institution responsible for implementation (coordination of implementation) of the measure: Ministry of Finance - Treasury administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  | Measure type: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) | Unit of measure |  |  |  |  | Source of verification |  | Initial value |  |  | Base year |  |  | Target value 2026 |  |  |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  |  | Target value 2030 |  |  |  |  |  |  |
| Drafted Public sector accounting improvement plan in accordance with IPSAS | Yes No |  |  |  |  | Website of Treasury administration |  | No |  |  | 2025 |  |  | - |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity name: |  |  |  | Deadline for completion of the activity |  | Institution responsible for implementation |  | Partners in the implementation of activity |  |  |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  | Link to programme budget (PR-PA/PJ) |  |  | 2026 |  |  |  |  |  |  | 2027 |  |  |  |  |  | 2028 |  |  |  |  |  | 2029 |  |  |  |  |  |  | 2030 |  |  |  |  |
| 5.2.1 Development of the Public Sector Accounting Improvement Plan in line with IPSAS, including a plan for improving IT systems. |  |  |  | Q4 2028 |  | Treasury administration |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |
| 5.2.2 Provision of IPSAS translations. |  |  |  | Q4 2028 |  | Treasury administration |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2.3 Enhancement of the capacities of employees in the Treasury Administration for IPSAS implementation, including study visits to countries with successful IPSAS adoption. |  |  |  | Q4 2028 |  | Treasury administration |  | Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # SPECIFIC OBJECTIVE VI: EXTERNAL OVERSIGHT OF PUBLIC FINANCES ENHANCED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at specific objective level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  | Initial value |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |  |  |
| Percentage of audited public fund beneficiaries with deficiencies in the internal control system |  |  |  |  |  | Percentage (%) |  |  |  | Report on the works of SAI |  |  |  |  | 85 |  |  |  |  | 2024: |  |  |  | 84 |  |  |  |  |  |  | 83 |  |  |  |  |  |  | 82 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Меasure 6.1: Strengthening the efficiency and impact of external audit through the integration of modern technologies, improvement of methodology and communication with stakeholders. ## Institution responsible for implementation (coordination of implementation) of the measure: State audit institution. Implementation period: 2026-2030; Measure type: Institutional management organizational. I Indicator(s) at measure level (outcome indicator); Unit of measure; Source of verification; Initial value; Base year; Target value 2026; Target value 2027; Target value 2028; Target value 2029; Target value 2030. Percentage of DRI recommendations implemented within 2 years of the publication of the report; Percentage (%); Internal reports on tracking the implementation of SAI recommendations; 75; 2025; 77; 79; 81. Activity name:; Deadline for completion of the activity; Institution responsible for implementation; Partners in the implementation of activity; Financial resources. Source of funds; Link to programme budget (PR-PA/PJ); 2026; 2027; 2028; 2029; 2030. 6.1.1 Development and adoption of guidelines for performance and compliance audits, along with regular training for auditors in performance auditing; Q4 2026 Continued trainings; SAI; SAI – Audit methodology and development department; Audit department; Budget funds; 1601-0401-0010-000; -; -; -; -; -. 6.1.2 Development of a methodology for selecting and conducting follow-up audits to monitor the implementation of recommendations.; Q4 2027; SAI; SAI – Audit services; Budget funds; 1601-0401-0010-000. 6.1.3 Creation of an internal database of good practices and typical findings; Q2 2027; SAI; SAI – Audit methodology and development department; ICT department; Budget funds; 1601-0401-0010-000. 6.1.4 Integration of modern technologies in auditing through development and implementation of automated audit tests, piloting artificial intelligence in auditing and introduction of digital platforms for collaboration and data sharing within audit teams; Q4 2028 continued; SAI; SAI – ICT department; External providers; IDI/EUROSAI; Budget funds/Donor funds; 1601-0401-0010-000; -; -; -; -; -. |
| ## Меasure 6.2: Ensuring effective parliamentary oversight over public finances |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Institution responsible for implementation (coordination of implementation) of the measure: National assembly – Committee on Finance, state budget and control of public spending |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Implementation period: 2026-2030 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ## Measure type: Institutional management organizational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  |  |  |  |  | Unit of measure |  |  |  | Source of verification |  |  |  |  | Initial value |  |  |  |  | Base year |  |  |  | Target value 2026 |  |  |  |  |  |  | Target value 2027 |  |  |  |  |  |  | Target value 2028 |  |  |  |  | Target value 2029 |  |  |  |  |  |  | Target value 2030 |  |  |  |
| Percentage of DRI reports reviewed in the National Assembly |  |  |  |  |  | Percentage (%) |  |  |  | Reports and minutes of the National assembly Finance committee |  |  |  |  | 50 |  |  |  |  | 2025 |  |  |  | 55 |  |  |  |  |  |  | 60 |  |  |  |  |  |  | 65 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of Committee meetings/sessions held for reviewing recommendations for amendments to laws in the presence of DRI and the Ministry of Finance, annually |  |  |  |  |  | Number |  |  |  | Minutes of the session/meeting |  |  |  |  | 1 |  |  |  |  | 2025 |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity name: |  |  |  |  |  | Deadline for completion of the activity |  | Institution responsible for implementation |  | Partners in the implementation of activity |  |  | Financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Source of funds |  |  |  |  |  |  | Link to programme budget (PR-PA/PJ) |  |  |  | 2026 |  |  |  |  |  |  | 2027 |  |  |  |  |  |  | 2028 |  |  |  |  | 2029 |  |  |  |  |  |  |  |  | 2030 |  |
| 6.2.1 Holding Committee and Subcommittee sessions for reviewing DRI audit reports, outside the National Assembly premises |  |  |  |  |  | Q4 2028 |  | National assembly – Committee on Finance, state budget and control of public spending – Subcommittee for reviewing SAI audit reports |  | State audit institution |  |  | Budget funds Donor funds |  |  |  |  |  |  | 2101-0003 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.2.2 Holding joint sessions of the competent parliamentary committees to review performance audit reports |  |  |  |  |  | Q4 2028 |  | National assembly – Committee on Finance, state budget and control of public spending – Subcommittee for reviewing SAI audit reports and other competent committees |  | State audit institution |  |  | Budget funds |  |  |  |  |  |  | 2101-0003 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.2.3 Organizing public hearings regarding the presentation of the Draft Budget Law and the Draft Law on the Budget Final Account |  |  |  |  |  | Q4 2028 |  | National assembly – Committee on Finance, state budget and control of public spending |  | Ministry of Finance, State audit institution, Fiscal council and National bank of Serbia |  |  | Budget funds Donor funds |  |  |  |  |  |  | 2101-0003 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

INTOSAI development initiative

EUROSAI – European organization of supreme audit institutions