Terms of Reference

Consultant for analysis of existing training programs with recommendations for the Treasury Department

for

Improving Public Financial Management for the Green Transition Project

## Background

Improving Public Finance Management for a Green Transition in the Republic of Serbia is a four-year Operation supported by the World Bank and AFD, which aims to assist the Government of the Republic of Serbia in strengthening its capacity for public finance management and implementing green investments. The key implementing institutions, in addition to the Ministry of Finance, are the Ministry of Environmental Protection, the Republic Property Directorate, the Secretariat for Public Policies, and the Public Procurement Administration.

The operation consists of two components:

1) Programme for Results (PforR), a component (Programme) consisting of two result areas:

• 	Strengthen fiscal resilience, transparency and effectiveness of spending – focused on further strengthening fiscal resilience, using public expenditure management to improve efficiency and focus on results, improving the ability to link plans and budgets through stronger costing at the planning stage, improving fiscal transparency, and improving the preparation of public investment projects.

• 	Greening the spending cycle in Serbia and developing selected other institutions for greater environmental resilience – focused on introducing and using green criteria in PFM, PIM and public procurement, as well as strengthening systems for monitoring and reporting on GHG emissions from facilities.

2) Investment Project Financing (IPF) Component (Project) consisting of technical assistance to support implementing entities in achieving expected results. The IPF component will consist of technical assistance -- including training, capacity building and peer learning, support for stakeholder engagement, and support for Program management.

The development objective of the Operation is to improve the core public financial management functions and institutional capacities needed for Serbia's fiscal resilience and green transition. The Operation will support the following key public financial management functions: budgeting and strengthening the links between plans and budgets, public investment and asset management, and fiscal risk management.

Performance management aspects of the Operation

The Ministry of Finance aims to integrate sustainable practices and environmental issues into its budgeting process. As part of this initiative, a qualified Consultant for analysis of necessary training programs is sought to conducting a comprehensive assessment of existing training programs, institutional capacities, and skills gaps within the organization. This will include analyzing current competency frameworks, training delivery methods, and alignment with strategic and operational objectives. Based on the findings, the Consultant will identify priority capacity-building needs, propose targeted training interventions, and provide recommendations for improving the effectiveness, efficiency, and sustainability of training activities.

## Objective of the assignment

## The Consultant will carry out a comprehensive analysis of the existing training programs within the Treasury Administration in order to assess their overall structure, content, and relevance. This analysis will focus on identifying the effectiveness of current training activities, as well as key gaps, weaknesses, and areas for improvement. As part of the assessment, the Consultant will conduct a structured survey among employees to evaluate their satisfaction with completed training programs, perceived usefulness, and applicability of acquired knowledge in daily work.

## In parallel, the Consultant will assess the extent to which existing training programs are aligned with the principles and objectives of the Green Agenda. Furthermore, the Consultant will review and analyze all applicable regulations, internal acts, procedures, and rules related to training in order to ensure full compliance with legal and regulatory requirements. Based on the findings of these analyses, the Consultant will formulate clear, evidence-based recommendations on priority areas where additional, revised, or new training programs are required to strengthen institutional capacity and improve overall performance.

## Scope of Work

The Consultant will perform the following:

1) Conduct a comprehensive analysis of the existing training programs within the Treasury Administration, including their scope, structure, content, and delivery methods.

2) Identify the effects, strengths, weaknesses, and gaps of the current training programs, with particular attention to relevance, effectiveness, and practical applicability.

3) Design and implement a structured survey among employees to assess satisfaction with attended trainings, perceived quality of training content, and usability of acquired knowledge in daily work.

4) Analyze training participation rates, coverage across organizational units, and accessibility of training programs for different categories of staff.

5) Review and analyze all applicable laws, by-laws, internal acts, procedures, and rules related to training in order to ensure compliance with legal and regulatory requirements.

6) Examine the consistency between training programs and existing competency frameworks, job descriptions, and required skill sets within the Treasury Administration.

7) Identify overlaps, duplications, and inefficiencies in current training offerings and propose rationalization measures.

8) Assess the adequacy of training monitoring and evaluation mechanisms, including feedback collection and performance measurement practices.

9) Provide evidence-based recommendations on priority areas where new, revised, or additional training programs are required. Analysis of all past training programs implemented within the Treasury Administration, including their scope, methodology, relevance and effectiveness;

## Deliverables

The Consultant shall prepare and deliver the following in the corresponding stages of the assignment:

| Deliverables | Due dates |
| --- | --- |
| Deliverable 1: Analytical Report on Existing Training Programs; Conducted a comprehensive analysis of the existing training programs within the Treasury Administration; Identified the effects, strengths, weaknesses, and gaps of the current training programs. | 30 days after signing the contract |
| Deliverable 2: Employee Training Satisfaction Survey and Analysis Report; Designed and implemented a structured survey among employees to assess satisfaction with attended trainings, perceived quality of training content, and usability of acquired knowledge in daily work. | 60 days after signing the contract |
| Deliverable 3: Regulatory and Institutional Compliance Review; Reviewed and analyzed all applicable laws, by-laws, internal acts, procedures, and rules related to training in order to ensure compliance with legal and regulatory requirements. | 90 days after signing the contract |
| Deliverable 4: Training Needs and Skills Gap Analysis; Examined the consistency between training programs and existing competency frameworks, job descriptions, and required skill sets within the Treasury Administration; Identified overlaps, duplications, and inefficiencies in current training offerings and propose rationalization measures. | 120 days after signing the contract |
| Deliverable 5: Recommendations Report on Priority Training Areas; Provided evidence-based recommendations on priority areas where new, revised, or additional training programs are required. Analyzed all past training programs implemented within the Treasury Administration, including their scope, methodology, relevance and effectiveness. | 150 days after signing the contract |

## The selected Consultant shall be paid the lump sum contract amount linked to the deliverables.

Length of the assignment

The estimated Consultant’s time input is up to 100 working days in total until August 30, 2026. The intended start date of the assignment is April 2026.

This estimate is indicative and the Proposal shall be based on the Consultant’s own estimates for the same.

The Consultant shall deliver all the expected outputs at the daily rate that will be dependent on the qualifications, the market range for similar assignment, and previous candidate remuneration for similar services as well as approved project budget.

Reporting

The Consultant will report on his/her work to the Director of the Treasury Department.

The Consultant should take into consideration all relevant gender related issues in relation to the outputs of the assignment.

The Consultant will provide hard and electronic copies of any documents and technical materials developed during the Project in their original electronic PDF format. The reports will be provided in Serbian language.

Qualification Requirements

The Consultant must possess the following qualifications:

1) BsC degree in the field of economics or law at the basic academic studies (240 EPSB points);

2) Minimum 3 years of experience in the field of preparation and analysis of staff training;

3) Demonstrated professional experience in analyzing, evaluating, and designing training programs for a minimum of two different institutions or organizations

3) Experience in public finance management in various areas such as public finance, public procurement, restructuring, security etc.;

4) Previous work with financial institutions or government organizations will be considered an advantage;

5) Knowledge of working on a computer and in MS Office;

6) Knowledge of the English language will be considered an advantage;

7) Fluency, both written and verbal, in Serbian

8) Advanced user of MS Office;

9) Good analytical and communication skills will be considered an advantage;

10) Previous work on projects related to public finance will be considered an advantage.

Confidentiality

The Consultant undertakes to maintain the confidentiality of all information that is not in the public domain and will not be involved in any other task or project that presents a conflict of interest with the aforementioned project.

Inputs and responsibility of the Client

The client shall provide access to all necessary materials, methodologies and internal acts.

Selection

Consultant will be selected in accordance with the Open Competitive Selection of Individual Consultants as set out in the World Bank’s Procurement Regulations for IPF Borrowers: Procurement in Investment Project Financing – Goods, Works, Non-Consulting and Consulting Services (November 2020) and the World Bank's ‘Guidelines on Preventing and Combating Fraud and Corruption in Program-for-Results Financing’, dated February 1, 2012, and revised July 10, 2015.

The candidates will be evaluated applying the following evaluation criteria:

| General experience | 40 points |
| --- | --- |
| Specific Experience relevant to the Assignment | 60 points |
| TOTAL: | 100 POINTS |